## _Deals
Status | Deal Risk - Reason | Primary Site's Site Name | Project Name | Launch Year | Requestor Org | Project Type | Transaction Type | Location Address | Location City | Primary Site's State | Broker | Amazon TM | NEW Broker | Local Broker | Fee Developer | Landlord/Seller's Rep | Landlord/Seller | Debriefed? | Site Selected? | LOI Final? | Lease/PSA Final? | CAR Approved? | Notes
Inactive | N/A | DZE4_1 | 26_Bridge_NA_US_Leoma_DZE4_1 | 2026 | AMZL | New Launch | New Lease | 105 Jarvis Brewer Drive | Rogersville | AL | Andrea Roy |  | On Hold |  | N/A | [7 empty] | Project A;Shield clean up needed
Active | Medium - Business | 27_ABDN_4 | 27_ABDN_NA_US_Washington_27_ABDN_4 | 2027 | CF | New Launch | New Lease |  | Washington | DC | Andrea Roy | TBD | Flanigan | John Dettleff, JLL |  | TBD | TBD |  | N | N | N | N | Preliminary survey complete, options reviewed with business. No direction on next steps.
Active | Medium - Transaction | XBA5 | 26_XPT_NA_US_Washington DC_XBA5 | 2026 | AMZL | New Launch | New Lease |  | Washington DC | DC | Andrea Roy | Ashley Perkins | Andreya |  | N/A | [7 empty] | We haven't been formally assigned this and I have no actual requirement details. Ashley Perkins hit me up on slack last week about it so we will need to get a survey together. Actual requirement is an e-bike initiative currently operating out of a parking lot off M Street near Nationals Park. That site is about to be redeveloped and they will need another location. Recommend leveraging the parking team for this.
Active | Low | SLM1 | 28_SSD FC_NA_US_Wilmington_SLM1 | 2028 | R2L | New Launch | Internal Transfer | 101 Vitamin Drive (Placeholder Address) | Wilmington | DE | Andrea Roy | TBD | Cait | N/A | N/A | N/A | N/A |  | Y | N | N | N | Internal transfer of excess land at ILM1. Amazon has indicated that they intend to self develop this. Nothing for transactions to do, fully in Amazon's court. Original developer is Seefried and Greg Herren is aware both that the excess land is going to be developed and that Amazon is going to attempt to do it solo. He's standing by to step in if need be. Project code name is Grouper (ILM1= The Whale, DCD6 = Project Tuna).
Inactive | N/A | DZH8_3 | 26_Bridge_NA_US_Chattanooga_DZH8_3 | 2026 | AMZL | New Launch | New Lease | 534 Patterson Ave | Fort Oglethorpe | GA | Andrea Roy |  | Cancelled |  | N/A | [7 empty] | Project A;Shield clean up needed
Active | High - Regulatory, Approvals | SKY3 | 27_SSD FC_NA_US_Richmond-Berea_SKY3 | 2027 | R2L | New Launch | Purchase | 1501 McGrathiana Parkway (Placeholder Address) | Lexington | KY | Andrea Roy | Adam Knoll | Ashleigh | David Graves, Cypress | Dusten Estes & Leila Baker (Construction), Stonemont | David Kelly, CW (Cincinnati) | Multiple |  | Y | Y | Y | Pending | Site is an assemblage of two parcels owned by the City of Lexington, plus a smaller corner parcel owned by Lexington Equine Group. Land was initially owned by the University of Kentucky (UK) and transferred to the City in a land swap for City-owned land near campus. University of Kentucky has design approval rights and has been a nightmare to work with. We navigated our way through that and have design approval to proceed, conditioned on diverting tucks onto Citation Blvd to the south. We're in for formal approvals with KY Transportation Commission and all indications are that we're fine however approvals aren't forecasted until right around 4th of July and are triggering about $10M in additional site work. Developer is working on VE to bring that down. Issue feels largely put to bed and CAR is routing. DD on both purchases expire right about when we would have the KYTC approval and both sales are crossed (one cannot close without the other) and have approvals as a closing condition. From a transaciton stand point, the biggest risk is internal: TM is a bit of a loose cannon and developer isn't the strongest. I've coached them up as best I can but they need to get this over the finish line. Know that SSD is talking about redesigning this to increase the building size by 16K SF to accomodate some new under-the-roof requirement. Given how brutal design approvals were, that should be avoided at all costs.
Active | Medium - Business | DLE5-1 | 28_AMZL_NA_US_Lexington_DLE5-1 | 2028 | AMZL | New Launch | Purchase |  | Lexington | KY | Andrea Roy | TBD | Jason | David Graves, Cypress | N/A | TBD | TBD | N | N | N | N | N | Part of new POR. Pin is directly on top of current facility, which is leased and has significant term. Met with Topology to flesh out where the actual demand is coming from here and it's actually in Richmond, KY. Placement there impacts the RSR pin in London, KY. Topology is supposed to be re-running their model with the pin relocated to Richmond, KY to confirm size of facility needed.
Active | Medium - Business | DLK4-1 | 28_AMZL_NA_US_Louisville_DLK4-1 | 2028 | AMZL | New Launch | Purchase |  | Louisville | KY | Andrea Roy | TBD | Jason | Powell Spears, JLL | N/A | TBD | TBD | N | N | N | N | N | New POR with same call out as Lexington: Two leased facilities in market, both with term. Requested centroid is on top of both. No indication where this thing actually needs to be.
Active | Medium - Approvals | SKYY | 27_SSD FC_NA_US_Louisville_SKYY | 2027 | R2L | New Launch | New Lease | 8001 Air Commerce Drive | Louisville | KY | Andrea Roy | Mike Nevel | Jason | Powell Spears, JLL | N/A | Robert Walker, C&W | Adam Thomas, Louisville Airport Authority |  | Y | Y | Y | Pending | In for CAR, lease is substantially complete. There has been little to no precon engagement on this and precon has not reviewed any drawings. Keith Seo is legal and is shockingly willing to proceed on Transactions vetting that we are good with the base building standard. Biggest issue is zoning. Airport isn't bringin the ZCL through and Amazon cannot figure out how to file it themselves. I'm just going to do it and eat the $50 fee but know that what comes back will not be on the right form and will need to get cleaned up for execution.
Inactive | N/A | DTS4-1 | 27_RSR DS_NA_US_Middlesboro_DTS4-1 | 2027 | R2L | New Launch | New Lease |  | Middlesboro | KY | Andrea Roy |  | Jason | [9 empty] | Dropped off POR and is a blocked market regardless (severe topo, no population, legacy environmental -mostly coal).
Inactive | N/A | DOL2-1 | 28_RSR DS_NA_US_London_DOL2-1 | 2028 | R2L | New Launch | Purchase |  | London | KY | Andrea Roy | Frank Taylor | Jason | N/A | N/A | N/A | N/A |  | N | N | N | N | This is another 1W1F requirement however the original facility is a lease that is up in 2028 so a BTS would make a lot of sense here. Pin will be subject to topology analysis and placement of the Lexington AMZL pin. *If* we end up needing something here, use Powell Spears in Louisville to keep you legal and then call Paula Thompson with London-Laurel EDA. Best I've ever worked with, knows everyone, strong ally.
Active | Medium - Approvals | SDC5 | 28_SSD FC_NA_US_Washington_SDC5 | 2028 | R2L | New Launch | New Lease | 2300 Craftsman Circle | Hyattsville | MD | Andrea Roy | Mike Nevel | Emma | John Dettleff, JLL | N/A | Thomas Hinder, Newmark | Carson Goldman, Terreno |  | Y | Y | N | Pending | Lease is near to final, site is in for CAR. This is a 1:1 option for SSD and needs to be finalized. Precon for this site is contract and the contract wasn't renewed (clerical error on Amazon's part). They're back now but have not dug in on anything. Impacts to CAR & lease approval tbd.
Active | Low | DDI7 | 28_AMZ_NA_US_Washington DC_DDI7 | 2028 | AMZL | New Launch | Purchase | 8907 Gas House Pike | Frederick | MD | Andrea Roy | Richard Corley | Emma | John Dettleff, JLL | Chris Rodriguez (transaction) & Pete Torres (construction), Trammell Crow | Toby Mink, CBRE | Trammell Crow (Chris Rodriguez) | Y | Y | Y | Y | Y | Site was purchased. AMZL's design was horrific and they are in redesign to shift AMZL to accommodate colocation with SSD.
Inactive | N/A | DSB4-1 | 28_RSR DS_NA_US_Grantsville_DSB4-1 | 2028 | R2L | New Launch | Purchase |  | Grantsville | MD | Andrea Roy | Kristen De Famio | Emma | N/A | N/A | N/A | N/A |  | N | N | N | N | 1W1F requirement in a market where we have an Amazon-owned BTS. Developer on the original facility is SunCap. Kristen is working directly with them to evaluate expanding current vs building new. In the event that the business 1) keeps this requirement on POR, and 2) cannot expand, will need to work with Topology to determine where the demand leakage is. It makes zero sense to have two facilities in rural MD/WV.
Active | High - Business, Transaction | IADx | 28_RVL_NA_US_Raleigh_IADx | 2028 | RELO | New Launch | New Lease |  | Raleigh | NC | Andrea Roy | Phil Perri | Emma | Andrew Young, Colliers | N/A | N/A | N/A |  | N | N | N | N | Site was moving to site selection with a primary option (Regional Commerce Park, Sanford) and backup (Larkin Regional Commerce Center, Statesville) before the business moved the pin. Sanford site has already been cut loose and The Keith Corp was notified that Larkin is on hold pending validation of the new requirement. Revised survey is in raw form with inputs back from Chad's ARS survey, our legacy Charlotte survey and SC options from the ATL team (who were great to work with here). Larkin is still the preferred option. Materials being finalized for debrief 5/27 and site selection 6/23).
Active | High - Transaction, Approvals | SNC5 | 27_SSD FC_NA_US_Raleigh-Durham_SNC5 | 2027 | R2L | New Launch | New Lease | 501 North Greenfield Parkway (Placeholder Address) | Raleigh-Durham | NC | Andrea Roy | Mike Nevel | Emma | Andrew Young, Colliers | N/A | N/A | Tim Brent, Longleaf |  | Y | Y | N | Pending | Internal target for lease execution was 6/1. CAR white paper and comps completed 4/22 and have been sitting there since. Major issues on this one and Landlord is hot. Building in question is part of a two-building development with leased premises beign the first phase. Second phase was on target to go vertical end of month however Amazon ran a TIS, communicated directly with NCDOT for it and now NCDOT is requiring a TIS for the second phase of development. Landlord was not consulted on any of the NCDOT communication and Amazon was warned that Landlord did not want this to happen. All told, potential impact to 2nd phase is approximately 6 months. TM has also communicated that we're 2 months, not two weeks, from lease execution citing this traffic issue which exacerbated the situation.
Active | Medium - Business | DNR9-1 | 28_RSR DS_NA_US_Hickory_DNR9-1 | 2028 | R2L | New Launch | Lease (may convert to purchase) | 840 SW Complex Street | Lenoir | NC | Andrea Roy | Al Patel | Emma | Dave Hanna, Foundry Commercial | N/A | Derek Anderson, Binswanger | Malouf |  | Y | Y | N | N | Project A that converted to long term requirement. +/-500K SF Class C facility w/some LL upgrades to building. Location has been blocked for over 3 years due to topography (mountainous) and changing POR. LOI has been final for over 6 weeks; legal was finally onboarded last week. Transaction pace needs to significantly speed up to keep this on track.
Active | Medium - Transaction | CLT-A | 26_PA_NA_US_Charlotte_CLT-A | 2026 | Prime Air | New Launch | New Lease |  | Charlotte | NC | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Active | Medium - Transaction | Uptown Charlotte | 26_QC_NA_US_Charlotte_Uptown Charlotte | 2026 | Quick Commerce | New Launch | New Lease |  | Charlotte | NC | Andrea Roy | Mark Gillmore | Emma | Osler Woltz, Atlantic Retail |  | TBD | TBD |  | N | N | N | N | Requirement was pulled and pushed out. Local and TM have resurveyed and are starting to engage sites. Peer review only; they can handle this.
Active | Medium - Transaction | DT Raleigh | 26_QC_NA_US_Raleigh_DT Raleigh | 2026 | Quick Commerce | New Launch | New Lease |  | Raleigh | NC | Andrea Roy | Mark Gillmore | Emma | Osler Woltz, Atlantic Retail |  | TBD | TBD |  | N | N | N | N | Requirement was pulled and pushed out. Local and TM have resurveyed and are starting to engage sites. Peer review only; they can handle this.
Active | Medium - Transaction | DT Raleigh-b | 26_QC_NA_US_Raleigh_DT Raleigh-b | 2026 | Quick Commerce | New Launch | New Lease | 1415 South Bloodworth Street | Raleigh | NC | Andrea Roy | Mark Gillmore | Emma | Osler Woltz, Atlantic Retail |  | TBD | TBD |  | N | N | N | N | Requirement was pulled and pushed out. Local and TM have resurveyed and are starting to engage sites. Peer review only; they can handle this.
Active | Medium - Transaction | Uptown Charlotte-c | 26_QC_NA_US_Charlotte_Uptown Charlotte-c | 2026 | Quick Commerce | New Launch | New Lease | 2325 Freedom Drive | Charlotte | NC | Andrea Roy | Mark Gillmore | Emma | Osler Woltz, Atlantic Retail |  | TBD | TBD |  | N | N | N | N | Requirement was pulled and pushed out. Local and TM have resurveyed and are starting to engage sites. Peer review only; they can handle this.
Active | Medium - Transaction | DNR8-1 | 28_RSR DS_NA_US_Fayetteville_DNR8-1 | 2028 | R2L | New Launch | Purchase | 2740 Clark West Road (pending) | Fayetteville | NC | Andrea Roy | Frank Taylor | Emma | Andrew Young, Colliers | Ben Scerri, SunCap | TBD | SkyREM |  | N | N | N | N | Site debreifed and a single option - SkyREM's land adjacent to the Campbell's DC - was short listed. Moving negotiations to a phone call to finalize then papering over. SunCap had previously been awarded development and will continue on for this site. They're preparing a spend schedule in the background.
Transferred - Emma Remy |  | SFY1 | 28_SSD FC_NA_US_Fayetteville_SFY1 | 2028 | R2L | New Launch | Purchase | 5657 Bragg Boulevard (Placeholder Address) | Fayetteville | NC | Andrea Roy | Emma Remy | Emma | Andrew Young, Colliers | Hunter Nichols (Construction), Samet | Karl Hudson, Foundry Commercial | Private Family |  | Y | N | N | N | This has already transitioned to Emma with terms fully agreed to prior to transition. Site is just outside RDU4 and a great location for what we're tyring to do. We also have an RSR requirement in the same market. If SSD falters, try to swap RSR onto this site.
Inactive | N/A | HRD3 | 27_AMXL_NA_US_Raleigh_HRD3 | 2027 | AMXL | New Launch | Internal Transfer |  | Raleigh | NC | Andrea Roy | Laurie Matthews | Emma | N/A | N/A |  | N/A | Y | N | N/A | N/A |  | Requirement has been kicking around for years with no direction. Surveyed 3x, nothing can pass FA.
Inactive | N/A | DZO5_1 | 26_Bridge_NA_US_Boone_DZO5_1 | 2026 | AMZL | New Launch | New Lease | 840 SW Complex Street | Lenoir | NC | Andrea Roy | Al Patel | Emma | Dave Hanna, Foundry Commercial | N/A | Derek Anderson, Binswanger | Malouf | Y | Y | Y | N | N | Project A that converted to long term requirement. +/-500K SF Class C facility w/some LL upgrades to building. Location has been blocked for over 3 years due to topography (mountainous) and changing POR. LOI has been final for over 6 weeks; legal was finally onboarded last week. Transaction pace needs to significantly speed up to keep this on track.
Inactive | N/A | DZJ5_1 | 26_Bridge_NA_US_Hickory_DZJ5_1 | 2026 | AMZL | New Launch | New Lease | 725 Reese Drive SW | Conover | NC | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | US28702 | 26_Bridge_NA_US_Almond_DZD8_1 | 2026 | AMZL | New Launch | New Lease |  | Almond | NC | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | US28749 | 26_Bridge_NA_US_Little Switzerland_DZD9_1 | 2026 | AMZL | New Launch | New Lease |  | Little Switzerland | NC | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | RDU47 | 27_ATH Hub_NA_US_Durham_RDU47 | 2027 | ATS | New Launch | Purchase |  | Durham | NC | Andrea Roy | Phil Perri | Emma |  | N/A | TBD | TBD | N | N | N | N | N | Zombie requirement; been "on hold" for >1.5 years.
Inactive | N/A | RLD-B | 26_PA_NA_US_Raleigh_RLD-B | 2026 | Prime Air | New Launch | New Lease |  | Raleigh | NC | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Inactive | N/A | CLT-B | 26_PA_NA_US_Charlotte_CLT-B | 2026 | Prime Air | New Launch | New Lease |  | Charlotte | NC | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Inactive | N/A | RLD-A | 26_PA_NA_US_Raleigh_RLD-A | 2026 | Prime Air | New Launch | New Lease |  | Raleigh | NC | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Active | Medium - Construction | DFG1 | 27_AMZ_NA_US_CHATTANOOGA_DFG1 | 2027 | AMZL | New Launch | Purchase | 3400 Cummings Road | Chattanooga | TN | Andrea Roy | Frank Taylor | Emma | N/A | Shaun Cofer (construction) & Tom McCary (transaction), Scannell | N/A | Scannell (land flip) | Y | Y | Y | Y | Y | Shockingly, CAR was approved here. Moving to close by EOM.
Active | Low | ZTN2 | 26_QC_NA_US_Nashville_DT Nashville_ZTN2 | 2026 | Quick Commerce | New Launch | New Lease | 909 8th Avenue | Nashville | TN | Andrea Roy | Kevin Ray | Emma | JR Murphy, Echo Retail |  | Shelby Hall, Foundry | Private Family |  | Y | Y | Y | Pending | CAR submitted but not yet approved. Lease should be executed this week. Precon completely botched the design here and needs to re-do it. This is the dumbest requirement I have; make CJ run it.
Inactive | N/A | HKX2 | 26_XL DS_NA_US_Knoxville_HKX2 | 2026 | AMXL | New Launch | Internal Transfer | 3001 Knoxville Center Drive | Knoxville | TN | Andrea Roy | Laurie Matthews | Emma | N/A | N/A |  | N/A | Y | Y | N/A | N/A |  | This is an internal transfer that has been "in process" for two years. Nothing to be done.
Inactive | N/A | DZH8_2 | 26_Bridge_NA_US_Chattanooga_DZH8_2 | 2026 | AMZL | New Launch | New Lease | 70 Bob Ray Dr | Chattanooga | TN | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | DZH8_4 | 26_Bridge_NA_US_Chattanooga_DZH8_4 | 2026 | AMZL | New Launch | New Lease | 2685 Riverport Rd | Chattanooga | TN | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | DZJ6_3 | 26_Bridge_NA_US_Johnson City_DZJ6_3 | 2026 | AMZL | New Launch | New Lease | 110 Thomas Road | Bristol | TN | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | DZJ6_4 | 26_Bridge_NA_US_Johnson City_DZJ6_4 | 2026 | AMZL | New Launch | New Lease | 2165 Hwy. 75 | Blountville | TN | Andrea Roy |  | Emma |  | N/A | [7 empty] | Project A;Shield clean up needed
Inactive | N/A | BNA-A | 26_PA_NA_US_Nashville_BNA-A | 2026 | Prime Air | New Launch | New Lease |  | Nashville | TN | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Inactive | N/A | BNA-B | 26_PA_NA_US_Nashville_BNA-B | 2026 | Prime Air | New Launch | New Lease |  | Nashville | TN | Andrea Roy | Wes Thompson | Emma | [9 empty] | These were shelved and are now back. To be fair, I'm not engaged on these at all. TM also quit, unclear who will take over going forward.
Active | High - Financials | SRN1 | 28_SSD FC_NA_US_Roanoke_SRN1 | 2028 | R2L | New Launch | New Lease | 2040 Blue Hills NE Dr (pending) | Roanoke | VA | Andrea Roy | Emma Remy | Cait | N/A | Ben Scerri, SunCap | N/A | N/A |  | N | N | N | N | Owned land in Roanoke. Site is not selected; Amazon cannot get the development to pencil which indicates a volume problem, not a real estate problem. Pending site selection, SunCap was chosen as developer with Ben Scerri as lead.
Active | High -Transaction | SLE1 | 28_SSD FC_NA_US_Leesburg_SLE1 | 2028 | R2L | New Launch | New Lease | Manassas Logistics Park Buildings 5 & 6 (pending) | Leesburg | VA | Andrea Roy | Mike Nevel | Cait | John Dettleff, JLL | N/A | N/A | Chris Rodriguez (transaction) & Pete Torres (construction), Trammell Crow |  | N | N | N | N | Amazon initially shortlisted Manassas Phase III as a potential BTS however there is no appetite on Ownership's part for that. Phase III Building 5 is the closest building to SSD's minimum requirements and modification of the building to expand depth can be done as a minor modification. During negotiation, it was flagged that operations are parking deficient and TM directed that we also negotiate for Buidling 6, solely for parking. Trammell is on board and terms are largely negotiated between KBC and Trammell. Clarion, however, is not aligned and is a major sticking point both on terms and also on pace of timing. Pushing for a direct call to close this out. Once we have line of sight into terms we can stand behind, need to send an updated cash flow with both buildings to TM for site selection.
Active | Medium - Business | DFR9 | 27_RSR_NA_US_Edinburg_DFR9 | 2027 | AMZL | New Launch | Purchase |  | Edinburg | VA | Andrea Roy | Al Patel | Cait | Grant Bates, Newmark | N/A | N/A | N/A | N | N | N | N | N | Requirement has been on hold pending confirmation of POR. AMZL is indicating they need to significantly expand capacity in this market. We have previously presented expansion in their current facility (taking leased premise to +/-50K SF) and been told that volumes do not support that. Issue was flagged to topology.
Active | Medium - Transaction | DVX5-1 | 28_AMZL_NA_US_Norfolk_DVX5-1 | 2028 | AMZL | New Launch | Purchase |  | Norfolk | VA | Andrea Roy | Kristen De Famio | Cait | Gregg Christoffersen, JLL | N/A | TBD | TBD | N - Scheduled 5/28 | N | N | N | N | New POR. Very limited options in market. Preliminary survey reviewed with Kristen; on debrief calendar 5/28.
Active | Low | DFR3 | 27_AMZ_NA_US_Richmond_DFR3 | 2027 | AMZL | New Launch | Purchase | TBD West Creek Parkway | Henrico | VA | Andrea Roy | Richard Corley | Cait | Matt Anderson, Range Commercial | Hunter Nichols (construction), Samet | N/A | West Creek Associates / Pruitt Family | Y | Y | Y | Y | Y | In construction and pending launch. Nothing further needed here.
Active | Low | SVA5 | 27_SSD FC_NA_US_Virginia Beach_SVA5 | 2027 | R2L | New Launch | Internal Transfer | 1795 Dam Neck Road (Placeholder Address) | Virginia Beach | VA | Andrea Roy | Chris Grimaldi | Cait | N/A | Bill Hudgins (construction), Hamilton | N/A | N/A |  | Y | N/A | N/A |  | Internal transfer of excess land at ORF4. Site is pad ready, Hamilton was developer on the primary site. There should be no issues but for traffice issues with ORF4 (namely their drivers consistently and repeatedly ignoring truck restrictions on residential roads).
Transferred - Bo Fulk |  | OVA8 | 27_1DC_NA_US_New Kent_OVA8 | 2027 | CF | New Launch | Purchase | I-64 & Emmaus Church Road | New Kent | VA | Bo Fulk | Steve Perkins | Cait | Matt Anderson, Range Commercial | [8 empty] | Bo Fulk is running this. Nothing to be done unless you want to pull it off Bo's plate, as well.
Inactive | N/A | RIC47 | 27_ATH Hub_NA_US_Colonial Heights_RIC47 | 2027 | ATS | New Launch | Purchase |  | Colonial Heights | VA | Andrea Roy | Phil Perri | Cait |  | N/A | TBD | TBD | Y | N | N | N | N | Fully negotiated offer for a site for this then the business pulled it. It's now a zombie requirement with nothing further to be done.
Active | High - Regulatory | DII9 | 27_RSR_NA_US_Charleston_(FKA WWV1)_DII9 | 2027 | R2L | New Launch | Purchase | 16401 Winfield Road | Fraziers Bottom | WV | Andrea Roy | Frank Taylor | Jason | Mike Thompson, RealCorp | Jacob Holdeman (construction), Scannell | N/A | David Hobba |  | Y | Y | Y | Y | This entire requirement has been a nightmare but it feels like it's coming to an end. Site has been subject to lawsuits and vocal opposition from a very small, very geriatric subset of the community, mostly connected with the wedding venue across the street. Oppo group has been engaged with SHPO, who is now requiring a side agreement with the opposition group.
Active | High - Transaction | DVW3-1 | 28_RSR DS_NA_US_Charleston_DVW3-1 | 2028 | R2L | New Launch | Purchase |  | Charleston | WV | Andrea Roy | Al Patel | Jason | Matt Clackson, CBRE | [8 empty] | Everything about this summary is wrong. Requirement is in Huntington, WV - not Charleston, WV - and it was cancelled until last week. It's now back and our formerly surveyed sites all have high WHS risk. With the challenges at the Charleston project, we were trending to another full state capacity evaluation exercise to determine how we service Huntington (Marshall) and Charleston (largest population center) in parallel. | bar: N to N
Inactive | N/A | DZK7_1 | 26_Bridge_NA_US_Huntington_DZK7_1 | 2026 | AMZL | New Launch | New Lease | 2301 Virginia Avenue | Culloden | WV | Andrea Roy |  |  |  | N/A: N/A | Project A; this was cancelled and needs to be removed.
Inactive | N/A | DZD7_1 | 26_Bridge_NA_US_Kingmont_DZD7_1 | 2026 | AMZL | New Launch | New Lease | 2600 Whitehall Boulevard | Whitehall | WV | Andrea Roy |  |  |  | N/A: N/A | Project A;Shield clean up needed
Inactive | N/A | US25082-2 | 26_Bridge_NA_US_Charleston_DUE1_2 | 2026 | AMZL | New Launch | New Lease | 150 57th St SE | Charleston | WV | Andrea Roy |  |  |  | N/A: N/A | Project A;Shield clean up needed
Inactive | N/A | US25082-4 | 26_Bridge_NA_US_Charleston_DUE1_4 | 2026 | AMZL | New Launch | New Lease | 559 29th Street West | Charleston | WV | Andrea Roy |  |  |  | N/A: N/A | Project A;Shield clean up needed
Inactive | N/A | US25082-3 | 26_Bridge_NA_US_Charleston_DUE1_3 | 2026 | AMZL | New Launch | New Lease | 145 Iron Horse Drive | Charleston | WV | Andrea Roy |  |  |  | N/A: N/A | Project A;Shield clean up needed
!!! CALL OUT !!! I DO NOT KNOW WHAT THESE SITE CODES ARE; THEY ARE NEW
|  | SDC4-2 | 27_SSD FC_NA_US_Washington_SDC4-2 | 2027 | R2L | New Launch | New Lease |  | Washington | DC | Andrea Roy | [11 empty] | I have no idea what this but can guarantee it's not happening in 2027 if it's new.
|  | SDC6 | 28_SSD FC_NA_US_Washington_SDC6 | 2028 | R2L | New Launch | New Lease |  | Washington | DC | Andrea Roy
|  | SDCA | 28_SSD FC_NA_US_Washington_SDCA | 2028 | R2L | New Launch | New Lease |  | Washington | DC | Andrea Roy
ACTIVE AND NOT CURRENTLY IN SHIELD
Active | High - Transaction | SDC1 |  |  | R2L | Renewal & Expansion | New Lease | 6885 Commercial Drive | Springfield | VA | Andrea Roy | Wes Thompson |  | John Dettleff, JLL | N/A: N/A; TBD: TBD; TBD: Lauren Huber, ARES | 10-year renewal terms have been agreed to with a cash flow and term sheet provided to Wes, Trace, Nevel and John Dalton. The new term gives us expansion rights for the neighboring tenant (Daikin)'s space. We are simultaneously negotiating for a relocation and termination of Daikin now however this process has stalled as Daikin works through a brokerage issue (they have a national rep w/no local experience, local team wants to - and should - use CBRE; they're working through it). John Dettleff identified replacement space for Daikin and we sent them both an unsolicited proposal for that space along with a buyout offer of $1M to assist in relocation. Internally, we've signaled that a reasonable payment here would be up to $2M so we do have room before the deal falls apart. All indications are that they like the plan, love the space and want out, they just need to do some housekeeping to engage. Chirstie Lee at CBRE will be point for Daikin, ARES is taking a handsoff approach but is also broadly supportive and John Dettleff has been point to keep our hands clean. We just need to get to a point that we can engage and finish this. VERY high priority given lack of space availability.
Active | High - Environmental | SDCx |  | 2028 | R2L | New Launch | New Lease | 8250 Eastern Ave | Baltimore | MD | Andrea Roy | Mike Nevel |  | Toby Mink, CBRE | N/A | Justin Mohler, CBRE | Mike Reddy, RREEF (as DWS) | Y | N | N | N | N | To be clear, KBC's recommendation was either Trade Point Atlantic or going back to DBA3 (Kelso Drive). Mike went rogue on debrief and presented this. Building itself isn't bad and circulation is great. It's directly across the street from Back River Wastewater Treatment Plant, the largest in the state. There is a long history of environmental issues and the entire plant was placed under consent decree within the last 5 years. Amazon did 30 days of air quality testing which recently completed. No one has seen the final report but Mike is pushing ahead with site selection. I've been slow rolling terms to allow the deal to catch up with the transaction but requested an all hands with RREEF/DWS to finalize so we can transition this cleanly. The main point of contact at RREEF is a dream. Very reasonable, deal focused, sticks to the big issues. His asset management team, DWS, are very german and very in teh weeds. It's a struggle to beat back DWS but I have confidence in Reddy and Toby's team is very familiar with this building. Will need to be site selected. This is likely one of the newly renamed site codes, I just can't tell you which.

## _Prospects
Site Data | [6 empty] | Site Contact |  |  |  | Amazon
MSA | Address | City | State | Building or Land? | SF | Acres | Name | Firm | Phone | Email | Sourced By? | Subagency? | Potential Business Line | Presented? | To? | Notes
Washington, DC | 7501 Muirkirk Rd | Beltsville | MD | Land | N/A | 107.63 | Dennis Perkins | Civitas | 202-494-2054 | dperkins@civitasre.com | John Detleff, JLL | No, off market | Multiple | Y | Arman Fashandi, Mike Nevel, Darnell Tyler | Howard University's Beltsville Campus. Legacy IE zoning supports a wide array of industrial uses. Howard will not sell but will ground lease the site. Broker (Dennis Perkins, Civitas) also represents University of DC, which owns the neighboring site. Potential to expand purchase area with excess land to the south.
Washington, DC | 2800 Tower Oaks Blvd | Rockville | MD | Building | 113020 | 9.07 | Scott Kauffman | JM Zell | 202-256-3981 | skauffman@jmzell.com | John Detleff, JLL | No, off market | SSD | Y | Mike Nevel | 113K sf w/250 parking spaces, 6 docks, 1 drive-in. Zoned MXE which allows for "light industrial". Need local land use to weigh in on whether or not SSD conforms, zoning code is very ambiguous when it comes to use classifications. I've coveted this site for years. Near immediate access to I-270, surrouned by residential but buffeted on all sides by wetlands/trees that limit noise. One of the few existing buildings that can even remotely support Amazon's operations in Montgomery County. Presented with urgency to Mike Nevel, who blew it off. This site should be priority 1 of 1 for Amazon in DC. It's that critical.
Washington, DC | 1500 Eckington NE Place | Washington | DC | Building | 342902 | 2.93 | Carmen Perkins | Civitas | 202-494-2074 | cperkins@civitasre.com | N/A | No, off market | SSD | N |  | CONFIDENTIAL - Sirius is shopping their HQ in DC offmarket. Class B/C mixed use building w/legacy 2nd gen data center space on ground floor. This would be tough one to make work for last mile but the type of opportunity we should be elevating given zoning, location. If Amazon passes, would be an interesting opportunistic play with a group like Trammell, SunCap or Greystar who can work in the mixed use space.
Charlotte, NC | 10401 Monroe Road | Mathews | NC | Building | 877000 | 63 | Chris Draper | GA Group | 708-752-2774 | cdraper@gagroup.com | N/A | No, off market | Middle Mile (short term), AMZL (long term) | Y | Troy Zawadski, Phil Perri, Todd Jones (KBC) | Building sits in the gap in Amazon's Charlotte network in SE Charlotte. Size and proximity to freeway are limiting buyer demand creating a really interesting distress opportunity to purchase a facility in Charlotte at attractive pricing. Building is somewhat functional now but true value is in site, parking.
Norfolk, VA | 615 Bland Blvd | Newport News | VA | Building | 375556 | 27.4 | Will Bradley | Newmark | 410-299-0367 | will.bradley@nmrk.com | Gregg Christoffersen, JLL | Yes | AMZL | Y | Kristen De Famio | Site was on the list for the Norfolk AMZL requirement but TM shows a strong preference for land. Site in question makes way too much sense for Amazon. Developed to the maximum the site allows given wetlands, in place heavy power, signalization, three points of access. Building should be considered a scrape vs a reposition. Factoring in net zero storm water on new development, AMZL cannot build as much on site as this thing has and the legacy impervious is worth "overpaying" for. As a site, best in the Norfolk MSA on the peninsula. Strategic acquisition.