## First & Middle Mile
Action Item |  | Template &/ Training
Market Survey - Preparation with Local Broker
FALSE | Upon receipt from local broker, confirm the survey is in the proper survey template & the KMZ is up to KBC standards. The KMZ should mirror the excel survey. | Survey Templates
Survey KMZ_Training Guide_KBC
AMZN Transaction Docs Overview
FALSE | If there is any missing information from the survey, please pull data from (1) flyers in ReThink and then (2) CoStar. | Rethink
CoStar
FALSE | Confirm the comps are in the proper template. | Comps Templates
AMZN Transaction Docs Overview
FALSE | Add prior flash WHS results to the survey by referencing the Phase 0 DD Tracker. | Phase 0 DD Tracker
FALSE | Add prior labor results to the survey by referencing the Labor Master Tracker. | HR Labor Analysis Master Tracker 2026
FALSE | Save the excel survey, KMZ, flyers and comps in the Pre-Site Selection folder in WorkDocs.
FALSE | Schedule survey review with local broker, KBC Broker & the DM. FIRST MILE: Include tdjone@amazon.com and nicolrz@amazon.com MIDDLE MILE: Include donflan@amazon.com and flomacke@amazon.com
FALSE | Remind your broker to initiate subagency agreement. | Subagency - Tenant Representation
Market Survey - Preparation without Local Broker
FALSE | Export properties from Scout that meet the BRS requirement provided by the program team. | How to Guide - Property Export
FALSE | If there is any missing information from the exports, please pull data from (1) flyers in ReThink and then (2) CoStar. | Rethink
CoStar
FALSE | Confirm with Broker which sites from the exports should be included in the survey.
FALSE | Prepare the excel survey using the proper survey template. | Survey Templates
AMZN Transaction Docs Overview
FALSE | Prepare the survey KMZ. The KMZ should mirror the excel survey. | Survey KMZ_Training Guide_KBC
FALSE | Circulate the survey to the Broker to add pricing estimates & comments for each property
FALSE | Export comps from Scout. Confirm the search parameters with Broker. | How to Guide - Comps Export | Coming soon
FALSE | Confirm the comps are in the proper template. | Comps Templates
AMZN Transaction Docs Overview
FALSE | Add prior flash WHS results to the survey by referencing the Phase 0 DD Tracker. | Phase 0 DD Tracker
FALSE | Add prior labor results to the survey by referencing the Labor Master Tracker. | HR Labor Analysis Master Tracker 2026
FALSE | Save the excel survey, KMZ, flyers and comps in the Pre-Site Selection folder in WorkDocs.
FALSE | Schedule survey review with local broker, KBC Broker & the DM. FIRST MILE: Include tdjone@amazon.com and nicolrz@amazon.com MIDDLE MILE: Include donflan@amazon.com and flomacke@amazon.com
Market Survey - Survey Review
FALSE | Take notes during the survey review with DM in the "Survey Review Notes" section; making note of follow up items the survey review date and which sites were short listed sites; save updated survey to WDs. | Selection Status Definitions
FALSE | Circulate survey review notes to the DM, KBC Broker, and Broker Lead / PM via email.
FALSE | Send survey with review notes & KMZ to data@ to update Rethink and LENS.
FALSE | Actualize Market Survey Date in Shield.
Post Survey Review - Phase 0 Due Dilience
FALSE | Request labor with aleseife@amazon.com. | How to Guide - Labor Process
FALSE | Request flash WHS in LENS. | How to Guide - Flash WHS
FALSE | Add site addresses requested for flash WHS sites to the Phase 0 DD Tracker. | Phase 0 DD Tracker
Site Tour
FALSE | Please connect with your Program Manager for direction on Tour Books.
FALSE | Save final tour book to Pre-Site Selection folder
FALSE | If applicable, help coordinate a tour between local broker and DM.
FALSE | Actualize Site Tour Date in Shield
Pre-Site Selection - Phase 0 Due Diligence
FALSE | Upon receipt, add labor results to the survey. Labor results are distributed by aleseife@ via email. | How to Guide - Labor Requests
FALSE | Upon receipt, add flash WHS results to the survey. Flash WHS results are sent via email and generated by LENS. | How to Guide - Flash WHS Requests
FALSE | Re-circulate the survey with Phase 0 DD (Labor and Flash WHS) to the DM and broker.
FALSE | Save flash WHS results to the Due Diligence folder. Create individual site folders for the short list initial DD.
FALSE | Add flash WHS results to the Phase 0 Due Diligence tracker. Hyperlink results to WorkDocs. | Phase 0 DD Tracker
FALSE | Create a sub folder for LL Due Diligence within DD Project Folder and save any landlord provided DD.
FALSE | Request a test fit as directed by DM. | How to Guide - Test Fit Requests (First & Middle Mile)
How to Guide - ACS Single Scope DD Guide
FALSE | Save test fit in the Pre-Site Selection folder.
FALSE | Overlay test fit upon receipt and save in the Pre-Site Selection folder (if applicable). | Step 6-7 in Debrief KMZ Training Guide
FALSE | Flash Power *Auto generated upon addition to LENS. | How to Guide - LENS
FALSE | Crime *Auto generated upon addition to LENS. | How to Guide - LENS
FALSE | Natural Hazards *Auto generated upon addition to LENS. | How to Guide - LENS
FALSE | Employee Relations *Auto generated upon addition to LENS. | How to Guide - LENS
Pre-Site Selection - SEW Preparation
FALSE | Complete the SEW document. File path to be sent by Program Manager. | SEW Document Guide
SEW Template
FALSE | Complete lease scenario cash flow. Confirm terms with the latest LOI / your broker. *Not required for land purchases. | AMZN Transaction Docs - Cash Flows
FALSE | Ensure comps have been normalized and reviewed/approved by the DM. Include a comps map (see slides 13-14 in the SEW Document Guide for instructions). | AMZN Transaction Docs - Comps
FALSE | Complete reasons for passing on the alternative sites tab by confirming with your broker. Use drop down in template for the reasoning.
FALSE | Add ROM estimate sent from Program Manager.
FALSE | Save 3-4 market reports in the Site Selection folder, including one from CoStar. Create a Market Reports sub-folder within the project folder. W:\Shared With Me\Ops RE Transactions\CORE (GCF)\xSITE SELECTION | How to Guide - Pulling Market Reports
Post Site Selection - Phase 1 Due Diligence
*Upon PMO notes distribution, kick off the following Due Diligence items. Ensure all DD results are saved to the Due Diligence folder and Shield is updated. |  | Example Notes Distribution
FALSE | Create a KMZ of the selected site with the parcel information included. | How to Guide - Site Selected KMZ Creation
FALSE | Migrate materials from Pre-Site Selection folder to their respective folders. | See WDS Organization Tab
FALSE | Add flash WHS and labor results for subject site into Shield. | How to Guide - Labor and Flash WHS in Shield
FALSE | Order Title *Leases only. Outside counsel to order for purchases. | How to Guide - Title
How to Guide - ACS Single Scope DD Guide
FALSE | Order Power Assessment | How To Guide - Power Due Diligence
How to Guide - ACS Single Scope DD Guide
FALSE | Order Full Zoning report. | How to Guide - Zoning Report
How to Guide - ACS Single Scope DD Guide
FALSE | Order a Phase I Environmental Report. | How to Guide - Phase I
How to Guide - ACS Single Scope DD Guide
FALSE | Order Short Form Noise Study. *Leases only. Developer to order for purchases. | How to Guide - Noise Study
How to Guide - ACS Single Scope DD Guide
FALSE | Order Flash Traffic Study. *Leases only. Developer to order for purchases. | How to Guide - Traffic Reports
How to Guide - ACS Single Scope DD Guide
FALSE | Order Phase II Environmental Report. *As Needed Post Site Selection
FALSE | Order Long Form Noise Study. *As Needed Post Site Selection. Leases only. Developer to order for purchases. | How to Guide - Noise Study
How to Guide - ACS Single Scope DD Guide
FALSE | Order Full Traffic Study (TIA). *As Needed Post Site Selection. Leases only. Developer to order for purchases. | How to Guide - Traffic Reports
How to Guide - ACS Single Scope DD Guide
FALSE | Order a Property Condition Report (PCR). *Existing buildings only > 10 years old | How to Guide - PCR
How to Guide - ACS Single Scope DD Guide
LOI
FALSE | Draft LOI as requested by broker. *LOIs are sent before Site Selection as directed by DM and Broker. | LOI Templates
FALSE | Save each iteration of the LOI as negotiations progress to WDs
FALSE | Save final LOI in Selected Site folder in WorkDocs.
FALSE | Send the final LOI to data@ to update Rethink.
FALSE | Add the purchase price, square footage/acreage, and year building (existing only) into Shield. | How to Guide - Update Shield with LOI Terms
FALSE | Actualize the LOI date in Shield.

## AMZL & RSR & SSD
Action Item |  | Template &/ Training
Market Survey - Preparation with Local Broker
FALSE | Upon receipt from local broker, confirm the survey is in the proper survey template & the KMZ is up to KBC standards. The KMZ should mirror the excel survey. | Survey Templates
Survey KMZ_Training Guide_KBC
AMZN Transaction Docs Overview
FALSE | If there is any missing information from the survey, please pull data from (1) flyers in ReThink and then (2) CoStar. | Rethink
CoStar
FALSE | Confirm the comps are in the proper template. | Comps Templates
AMZN Transaction Docs Overview
FALSE | Save the excel survey, KMZ, flyers and comps in the Pre-Site Selection folder in WorkDocs
FALSE | Schedule survey review with Broker & DM
FALSE | Remind your broker to initiate subagency agreement | Subagency - Tenant Representation
Market Survey - Preparation without Local Broker
FALSE | Export properties from Costar that meet the BRS requirement provided by the program team. | How to Guide - Property Export
FALSE | Export properties from Scout that meet the BRS requirement provided by the program team.
FALSE | If there is any missing information from the exports, please pull data from (1) flyers in ReThink and then (2) CoStar. | Rethink
CoStar
FALSE | Confirm with Broker which sites from the exports should be included in the survey
FALSE | Prepare the excel survey using the proper survey template. | Survey Templates
AMZN Transaction Docs Overview
FALSE | Prepare the survey KMZ. The KMZ should mirror the excel survey. | Survey KMZ_Training Guide_KBC
FALSE | Circulate the survey to the Broker to add pricing estimates & comments for each property
FALSE | Export comps from Scout. Confirm the search parameters with Broker. | How to Guide - Comps Export | Coming soon
FALSE | Export comps from Costar. Confirm the search parameters with Broker.
FALSE | Confirm the comps are in the proper template. | Comps Templates
AMZN Transaction Docs Overview
FALSE | Save the excel survey, KMZ, flyers and comps in the Pre-Site Selection folder in WorkDocs
FALSE | Schedule survey review with Broker and DM
Market Survey - Survey Review
FALSE | Take notes during the survey review with DM in the "Survey Review Notes" section; making note of follow up items the survey review date and which sites were short listed sites; save updated survey to WDs.
FALSE | Circulate survey review notes to the DM and KBC Broker via email.
FALSE | Send survey with review notes & KMZ to data@ to update Rethink and LENS.
FALSE | Actualize market survey in Shield
Site Tour
FALSE | Please connect with your Program Manager for direction on Tour Books.
FALSE | Save final tour book to Pre-Site Selection folder
FALSE | Actualize Site Tour Date in Shield
FALSE | If no site tour is being planned, please update SHIELD to remove the forecasted date & update the risk to N/A
Debrief
FALSE | Confirm the DM has added the site to the debrief schedule. * Notify PM that files are saved for Debrief | SSD Debrief Calendar
AMZL / RSR Debrief Schedule
FALSE | Create a folder in Pre-Site Selection folder titled "Debrief [08.07.2026] *The date of debrief
FALSE | Clean up the debrief survey so the file only has sites that will be preseneted in the meeting. Please confirm pricing is included.
FALSE | Create debrief KMZ per Debrief KMZ_Training Guide_KBC | Debrief KMZ_Training Guide_KBC
FALSE | Obtain Site Plans or CADs from Landlord, and saved to Workdocs | SSD only
FALSE | Attended the debrief call & be ready to drive during the presentation. *Coordinate with broker who will own screen sharing
FALSE | Actualize debrief in Shield
Post Debrief - Phase 0 Due Diligence
*Upon PM notes distribution, kick off the following Due Diligence items. Ensure all DD results are saved to the Due Diligence folder and Shield is updated.
FALSE | Test fit | Pre-Con – AMZL & RSR XMs – SSD
FALSE | Request flash WHS in LENS. | How to Guide - Flash WHS Requests
FALSE | Order Flash Traffic from KH. | How to Guide - ACS Single Scope DD Guide
How to Guide - Traffic Reports
FALSE | Order Flash Zoning report. | How to Guide - ACS Single Scope DD Guide
How to Guide - Zoning Report
FALSE | Flash Power *Auto generated upon addition to LENS | How to Guide - LENS
FALSE | Crime *Auto generated upon addition to LENS | How to Guide - LENS
FALSE | Natural Hazards *Auto generated upon addition to LENS | How to Guide - LENS
FALSE | Employee Relations *Auto generated upon addition to LENS | How to Guide - LENS
FALSE | Request existing DD from Landlord / Owner via email. Create a sub folder for LL Due Diligence within DD Project Folder and save any landlord provided DD.
FALSE | Kick off any additional DD as instructed per the Debrief Notes circulated by the PM
FALSE | Save all DD results to Due Diligence folder & update SHIELD
Pre-Site Selection - SSD
FALSE | Complete the SEW document | SEW Document Guide
SEW Template
| Complete lease scenario cash flow for existing/spec buildings. Confirm terms with the latest LOI / your broker. | AMZN Transaction Docs - Cash Flows
FALSE | Ensure comps have been normalized and reviewed/approved by the DM. | AMZN Transaction Docs - Comps
Pre-Site Selection - AMZL & RSR
FALSE | Inputs as requested by the DM & XM
Site Selection
Sites will be selected via the approval tool. PM's will notify the project group once a site is formally selected.
FALSE | Migrate materials from Pre-Site Selection folder to their respective folders. | See WDS Organization Tab
Post Site Selection - Phase 1 Due Diligence
*Upon PM notification, kick off the following Due Diligence items with DM alignment. Ensure all DD results are saved to the Due Diligence folder and Shield is updated.
FALSE | Order Short Form Noise Study. Leases only. Developer to order for purchases. | How to Guide - Noise Study
How to Guide - ACS Single Scope DD Guide
FALSE | Order Power Assessment | Tow To Guide - Power Due Diligence
How to Guide - ACS Single Scope DD Guide
FALSE | Order Title *Leases only. Outside counsel to order for purchases. | How to Guide - Title
How to Guide - ACS Single Scope DD Guide
FALSE | Order Full Zoning report. | How to Guide - Zoning Report
How to Guide - ACS Single Scope DD Guide
FALSE | Order a Phase I Environmental Report. | How to Guide - Phase I
How to Guide - ACS Single Scope DD Guide
FALSE | Order Phase II Environmental Report. *As Needed Post Site Selection
FALSE | Order Long Form Noise Study. *As Needed Post Site Selection. Leases only. Developer to order for purchases. | How to Guide - Noise Study
How to Guide - ACS Single Scope DD Guide
FALSE | Order Full Traffic Study (TIA). *As Needed Post Site Selection. Leases only. Developer to order for purchases. | How to Guide - Traffic Reports
How to Guide - ACS Single Scope DD Guide
FALSE | Order a Property Condition Report (PCR). *Existing buildings only >10 years old | How to Guide - PCR
How to Guide - ACS Single Scope DD Guide
LOI
FALSE | Draft LOI as requested by broker. *LOIs are sent after Debrief as directed by DM and Broker. | LOI Templates
FALSE | Save each iteration of the LOI as negotiations progress to WDs
FALSE | Save final LOI in Selected Site folder in WorkDocs.
FALSE | Send the final LOI to data@ to update Rethink.
FALSE | Add the purchase price, square footage/acreage, and year building (existing only) into Shield. | How to Guide - Update Shield with LOI Terms
FALSE | Actualize the LOI date in Shield.

## DD Matrix By Mile
KBC Owned & Managed DD Matrix | [6 empty] | Real Estate Required DD - Non-KBC Owned
| First Mile |  | Middle Mile |  | AMZL & RSR & SSD |  | All Miles
DD Item | Project Stage | Responsibility | Project Stage | Responsibility | Project Stage | Responsibility | DD Item | Phase | Responsibility
Labor | Post Survey Review | PC | Post Survey Review | PC | N/A | N/A | Site Concept Plan | Phase 0 | Pre Construction Manager
Flash WHS | Post Survey Review | PC | Post Survey Review | PC | Post Debrief | PC | JRR | Phase 0 | Pre Construction Manager
Test fit | Pre-Site Selection | PC | Post Debrief | PC | Post Debrief | AMZL / RSR – Pre-Con SSD – XMs | Econ Dev Engagement | Phase 0 | DM
Flash Power | Pre-Site Selection | LENS Auto Generated | Post Debrief | LENS Auto Generated | Post Debrief | LENS Auto Generated | Site Sketch Plan | Phase 1 | Design
Crime | Pre-Site Selection | LENS Auto Generated | Post Debrief | LENS Auto Generated | Post Debrief | LENS Auto Generated | Firm Site Plan Approved (FSP) | Phase 1 | Design
Natural Hazards | Pre-Site Selection | LENS Auto Generated | Post Debrief | LENS Auto Generated | Post Debrief | LENS Auto Generated | Firm Composite Design Approved (FCD) | Phase 1 | Design
Employee Relations | Pre-Site Selection | LENS Auto Generated | Post Debrief | LENS Auto Generated | Post Debrief | LENS Auto Generated | MHE Reconciliation | Phase 1 | Design
Flash Traffic | Post Site Selection | PC | Post Debrief | PC | Post Debrief | PC | Zoning Confirmation | Phase 1 | Pre Construction Manager
Flash Zoning | N/A | N/A | Post Debrief | PC | Post Debrief | PC | GSRA (Global Site Risk Assessment) SIM Score | Phase 1 | Pre Construction Manager
Short Form Noise | Post Site Selection | PC | Post Debrief *only for the primary site | PC | Post Site Selection | PC | Site Concept Plan | Phase 1 | Pre Construction Manager
Power Assessment | Post Site Selection | PC | Post Debrief | PC | Post Site Selection** | PC | (BSCA) Building & Site Conditions Assessment (Existing Buildings), (SCA) Site Conditions Assessment for BTS | Phase 1 | Pre Construction Manager
Title | Post Site Selection | PC – Lease Outside Counsel – Purchase | Post Site Selection | PC – Lease Outside Counsel – Purchase | Post Site Selection | PC – Lease Outside Counsel – Purchase | As-built Model (ABM) (EB and/or Spec buildings only) | Phase 1 | Pre Construction Manager
Full Zoning | Post Site Selection* | PC | Post Site Selection* | PC | Post Site Selection | PC | Preliminary Engineered Site Plan | Phase 1 | Pre Construction Manager
Phase I | Post Site Selection* | PC | Post Debrief *only for the primary site | PC | Post Site Selection | PC | Concept-Level Grading and Utility Plan | Phase 1 | Pre Construction Manager
Phase II | As Needed Post Site Selection | PC | As Needed Post Site Selection | PC | As Needed Post Site Selection | PC | Geotechnical Report Produced (Desktop Memo) | Phase 1 | Pre Construction Manager
Long Form Noise Study | As Needed Post Site Selection | PC – Lease Developer – Purchase | As Needed Post Site Selection | PC – Lease Developer – Purchase | As Needed Post Site Selection | PC – Lease Developer – Purchase | Site Summary Rating | Phase 1 | Pre Construction Manager
Full Traffic Study (TIA) | As Needed Post Site Selection | PC – Lease Developer – Purchase | As Needed Post Site Selection | PC – Lease Developer – Purchase | As Needed Post Site Selection | PC – Lease Developer – Purchase | Scope Baseline (Artifact) | Phase 1 | Pre Construction Manager
PCR | Post Site Selection | PC – Existing buildings ONLY | Post Site Selection | PC – Existing buildings ONLY | Post Site Selection | PC – Existing buildings ONLY | Site Access Request & LL Questionnaire Sent (Email template) | Phase 1 | Pre Construction Manager
*Timing of request varies by project | [6 empty] | Geotechnical Memo | Phase 1 | Pre Construction Manager
**Confirm with DM prior to ordering | [6 empty] | ALTA/TOPO Survey | Phase 1 | Pre Construction Manager
[7 empty] | Geotechnical Survey Conducted (bore holes) | Phase 1 | Pre Construction Manager
[7 empty] | Scope Development Work Session (Meeting) | Phase 1 | Pre Construction Manager
[7 empty] | Responsibility Matrix (Scope-Stakeholder; LL/Dev/GC) | Phase 1 | Pre Construction Manager
[7 empty] | Road Improvement Scope or Traffic Mitigation | Phase 1 | Pre Construction Manager
[7 empty] | Architect Site Plan Received | Phase 1 | Pre Construction Manager
[7 empty] | Architect Floor Plan (AFP) | Phase 1 | Pre Construction Manager
[7 empty] | (KODR) Kick Off Design Review | Phase 1 | Pre Construction Manager
[7 empty] | Permit Site Plan (PSP) | Phase 1 | Pre Construction Manager
[7 empty] | PrePermit Set Review (PPSR) | Phase 1 | Pre Construction Manager
[7 empty] | Permit Floor Plan (PFP) | Phase 1 | Pre Construction Manager
[7 empty] | EPA Stormwater | Phase 1 | RE/AM
[7 empty] | Project Feasibility | Phase 1 | Sr. Program Manager (PMO)
[7 empty] | Schedule Baseline/Re-Baseline | Phase 1 | TES PMO
[7 empty] | WHS ESA 1-2 | Phase 1 | WHS
[7 empty] | Large Load Study | Phase 1 | Pre Construction Manager

## RE Milestone Definitions
RE Milestone | First Mile Definition | Middle Mile Definition | SSD Definition | AMZL Definition | RSR Definition
Market Survey Date | Date the longlisted survey is reviewed with the KBC Broker and DM. | Date the longlisted survey is reviewed with the KBC Broker and DM. | Date the longlisted survey is reviewed with the KBC Broker and DM. | Date the longlisted survey is reviewed with the KBC Broker and DM. | Date the longlisted survey is reviewed with the KBC Broker and DM.
Site Tour Date | Date that the DM toured the MSA. | Date that the DM toured the MSA. | Date the DM and Broker toured the MSA | Date that the DM & Broker toured the MSA. | Date that the DM & Broker toured the MSA.
Debrief Date | N/A - not tracked for first mile. | Date the KBC shortlisted sites are presented to the buisness. | Date of the most recent presentation of shortlisted site opportunities | Date the most recent reviewed sites with the DM's are presented to the buisness. | Date the most recent reviewed sites with the DM's are presented to the buisness.
Site Selected | PLEASE ONLY REFORECAST.. PROGRAM MANAGER OWNS ACTUALZING THIS DATE Date of formal GCF Site Selection approval. NACF Site Selection occurs monthly on the second Thursday of every month (subject to change). | PLEASE ONLY REFORECAST.. PROGRAM MANAGER OWNS ACTUALZING THIS DATE Date of formal Site Selection. Approval differs per facility type: 1. Date of formal Site Selection review. Sites are selected live in the meeting. 2. Date that the shortlisted site is fully approved by all stakeholders via the approval tool | PLEASE ONLY REFORECAST.. PROGRAM MANAGER OWNS ACTUALZING THIS DATE Date the shortlisted site is fully approved by all required approvers in the Approvals Tool | PLEASE ONLY REFORECAST.. PROGRAM MANAGER OWNS ACTUALZING THIS DATE Date that the shortlisted site is fully approved by all stakeholders and formal approval is sent through the "last-mile-approvals" slack channel | PLEASE ONLY REFORECAST.. PROGRAM MANAGER OWNS ACTUALZING THIS DATE Date that the shortlisted site is fully approved by all stakeholders and formal approval is sent through the "last-mile-approvals" slack channel
LOI Date | Date that the Letter of Intent (LOI) terms are agreed to. | Date that the Letter of Intent (LOI) terms are agreed to. | Date the Letter of Intent (LOI) terms are agreed to | Date that the Letter of Intent (LOI) terms are agreed to. | Date that the Letter of Intent (LOI) terms are agreed to.
Purchase & Sale Agrmt Execution | Date that the Purchase & Sale Agreement (PSA) was fully executed.​ | Date that the Purchase & Sale Agreement (PSA) was fully executed.​ | Date the Purchase Purchase & Sale Agreement (PSA) was fully executed | Date that the Purchase & Sale Agreement (PSA) was fully executed.​ | Date that the Purchase & Sale Agreement (PSA) was fully executed.​
Closing Date | Date that Amazon officially closes on the property. | Date that Amazon officially closes on the property. | Date Amazon offically closes on the property | Date that Amazon officially closes on the property. | Date that Amazon officially closes on the property.
RE CAR Inputs | Date that the Real Estate Capital Appropriation Request (RE CAR) Inputs were sent to Capital Planning by DM. | Date that the Real Estate Capital Appropriation Request (RE CAR) Inputs were sent to Capital Planning by DM. | Date that the Real Estate Capital Appropriation Request (RE CAR) Inputs were sent to Capital Planning by DM. | Date that the Real Estate Capital Appropriation Request (RE CAR) Inputs were sent to Capital Planning by DM. | Date that the Real Estate Capital Appropriation Request (RE CAR) Inputs were sent to Capital Planning by DM.
RE CAR Approval | Date that the CAR was fully approved in the approval tool.​ | Date that the CAR was fully approved in the approval tool.​ | Date the CAR was fully approved in the approvals tool | Date the CAR was fully approved in the approvals tool | Date the CAR was fully approved in the approvals tool
ES Submitted Date | Date that the Executive Summary (ES) is launched in the approval tool by legal.​ | Date that the Executive Summary (ES) is launched in the approval tool by legal.​ | Date the Executive Summary is launched in the approval tool by legal | Date the Executive Summary is launched in the approval tool by legal | Date the Executive Summary is launched in the approval tool by legal
M10 Lease/Contract Approval (Lease Execution) | Date that the lease was fully executed. | Date that the lease was fully executed. | Date the lease was fully executed | Date that the lease was fully executed. | Date that the lease was fully executed.
Development Agreement Date | Date that the Development Agreement was fully executed.​ | Date that the Development Agreement was fully executed.​ | Date the Development Agreement was fully executed | Date that the Development Agreement was fully executed.​ | Date that the Development Agreement was fully executed.​

## WDs Organization
File Path Matrix
First Mile | CORE (GCF) | W:\Shared With Me\Ops RE Transactions\CORE (GCF)
Middle Mile | SORT CENTERS | W:\Shared With Me\Ops RE Transactions\NON CORE\SORT CENTERS
| RELO | W:\Shared With Me\Ops RE Transactions\NON CORE\RELO
Last Mile | RSR | W:\Shared With Me\Ops RE Transactions\NON CORE\Last Mile\RSR
| SSD | W:\Shared With Me\Ops RE Transactions\NON CORE\GSF\SSD
| AMXL | W:\Shared With Me\Ops RE Transactions\NON CORE\Last Mile\AMXL
| AMZL | W:\Shared With Me\Ops RE Transactions\NON CORE\Last Mile\AMZL
Sub-Folder | Pre-Site Selection | Post Site Selection
Survey - Pre-Site Selection | 1. Survey (excel file & KMZ) 2. Flyers 3. Comps 4. Create a Debrief folder & save down the materials if applicable a. Debrief KMZ b. Debrief survey c. Flyers d. Topology heatmap / table e. Debrief notes PM is responsible for moving post debrief. 5. Create sub-folders for Shortlisted sites and save down​ the following: Naming: Address, City, State Naming for AMZL: Site Code - Address, City, State a. LOIs​ b. Test Fits​ / Site Plans c. CADs​ d. KMZ outline​ 6. Proposal Comparison If applicable
Due Dilligence | 1. Create sub-folders for Shortlisted Sites and save down​ the following: Naming: Address, City, State Naming for AMZL: Site Code - Address, City, State a. Flash WHS​ b. Flash Power c. Crime d. Natural Hazards e. Employee Relations f. LL Provided DD​ – please create a "LL Provide DD" folder | 1. At site selection, please move all sub-folders to a new folder titled "xLonglist". The following should be saved as loose files in the due diligence folder: a. Title documents (leases) b. Power Study c. Full Zoning Report d. Phase I e. Short Form Noise Study f. Flash Traffic g. Phase II If applicable h. Long Term Noise Study If applicable, leases only. i. Full Traffic Study (TIA) If applicable, leases only. j. Property Condition Report If applicable, existing buildings only. k. ALTA Survey If ordered by PC. 2. WHS Approval 3. Tax Approvals 4. Final Zoning Memo
Selected Site | SSD ONLY – SEW that will be launched in the approval tool for site selection | *Migrate the following from Pre-Site Selection for the selected site ONLY 1. LOIs, saved with site code and date executed 2. KMZ outline with parcel ID 3. Site Selection Materials First Mile only. PM is responsible for moving post site selection. Other Items: 4. Early Access Agreement If applicable 5. Cost Reimbursement Agreement (CRA) If applicable. 6. Create an RFQ sub-folder & save down the following materials if applicable a. Responses from each developer b. Comparison c. Lead/DM email approval of developer selection 7. Final Executed Deal Documents Managed by Legal a. Fully Executed Lease b. Fully Executed PSA c. Buyer Settlement Statement Purchases only. d. Fully Executed Development Agreement BTS only. e. Work Order BTS only.
Drawings |  | *Migrate the following from Pre-Site Selection for the selected site ONLY 1. Test Fits 2. CADs
CAR |  | 1. Final Cash Flow with FMV 2. Final Comps 3. CAR White Paper Last mile only 4. Page 0 Narrative RELO only 5. CAR Approval
Approvals | N/A – folder will be removed in the future | N/A – folder will be removed in the future
Brokerage | N/A – folder will be removed in the future | N/A – folder will be removed in the future
BaseCamp | 1. Sub-Agency Agreement / Co-Brokerage Agreement | 1. Fully Executed Lease or PSA 2. Commission Agreement 3. Commission Calculation 4. FMV Calculation 5. Closing Statements/Settlement Statement Purchases only. 6. For BTS a. Dev Fee Agreement b. CAR Approval c. GMP Budget
Best Practices
- Always include today's date when saving files down.
- Do not save over or delete files. Always archive.

## BU POCs (hidden)
Business Unit | Role | Contact | Notes -- I get really scared that this is going to get out dated quick.....
First Mile | Team Lead | Nicole East
| Business Strategy Lead | Mo Camacho
| Development Manager Lead | Scott Montgomery
| Development Manager | Errol Tremolada
Eric Strauss
Rachel Elliot
Philip Ristevski
Reed Pankey
David Guest
| Lead Broker | Todd Jones
| Program Manager | Nicole Rasmussen
Middle Mile | Team Lead | Charlie Lohr
| Business Strategy Lead | Eleanor Aguilar
| Development Manager | Troy Zawadski
Phil Perri
| Lead Broker | Don Flanigan
| Program Manager | Mackenzie Floyd
AMZL & RSR & AMXL | Team Lead | Amber Matas
| Business Strategy Lead | Lauren McGowan
| Development Manager | Kristen DeFamio
Ashley Perkins
Dave Rende
David Guest
Manuel Medina
Chris Demco
Jordan Behar
Laurie McQueen
| Lead Broker | Michael Peabody
| Program Manager | Mackenzie Floyd Lauren Bays
SSD | Team Lead | Trace Blethen
| Business Strategy Lead | Lauren McGowan
| Development Manager | Adam Knoll
Christian Van
Dave Chojnowski
David Guest
Mike Nevel
| Lead Broker | Ashleigh Sundet
| Program Manager | Dominic Nichols
Quick Commerce | Team Lead | Jamie Stevenson
| Business Strategy Lead | Lauren McGowan
Development Manager
| Lead Broker | CJ Bowles
| Program Manager | Kristy Cole
Renewals | Team Lead | Mark Spector
| Business Strategy Lead | Lauren McGowan
| Development Manager | John Dalton
Mo Camacho
Laurie McQueen
Sam Bonacci
Sarah Casserly
| Lead Broker | Don Flanigan
| Program Manager | Max Madani

## Vendor SLAs
Vendor SLAs |  | Internal SLAs
Power Assessments |  | FLASH WHS
All Vendors |  | WHS
Power Assessment Report (PAR) | 3 weeks | FLASH WHS | 5 business days | WHS POC Map
Noise |  | Labor
Kimley Horn |  | WFS
Short Form Noise | 1 week | Labor | 10 business days - from the Friday of the week submitted
Long Form Noise | 2 weeks - if no data collection required; add 2 additional weeks if data collection required | FLASH Power
NV5 |  | LENs Generated
Short Form Noise | 10 business days | FLASH Power | Auto generated via LENs
Long Form Noise | 25 business days | Crime
Traffic |  | LENs Generated
Langan |  | Crime | Auto generated via LENs
Flash Traffic Assessment | 2 weeks | Nat Haz
Traffic Assessment | 2 to 3 weeks | LENs Generated
Traffic Impact Study (TIS) | 4 to 6 weeks depending on data collection for either the Client or Public TIS. | Nat Haz | Auto generated via LENs
| 2 to 3 additional weeks for both studies. Public TIS submission times can sometimes depend on getting in contact with the AHJ. | Employee Relations
TIS Peer Review | 2 weeks | LENs Generated
Kimley Horn |  | ER | Auto generated via LENs
Flash Traffic Assessment | 1 week | Phase I Revew
Traffic Impact Study (TIS) | 8 weeks | WHS
TIS Peer Review - 1 week | 1 week | Phase I Review | 5 business days | WHS POC Map
NV5 |  | Phase II Revew
Flash Traffic Assessment | 10 business days | WHS
Flash Traffic Assessment w/ site visit | 15 business days | Phase II Review | 5-10 business days | WHS POC Map
Traffic Impact Study (TIS) | 30-35 business days
TIS Peer Review | 1 week
Title
Chicago Title
Title Commitment | 15 business days
Property Condition Report
CBRE
PLSR | 10 business days from engagement w/ no sewer scoping. 15 days with sewer scoping
PCSR | 10 business days from engagement w/ no sewer scoping. 15 days with sewer scoping
BTSR | 10 business days from engagement w/ no sewer scoping. 15 days with sewer scoping
Environmental
Langan
Phase 1 | 2 weeks
Phase 1 Refresh | 1-2 weeks
Phase 2 | 4-5 weeks
Geosyntec
Phase 1 | 2 weeks
Phase 1 Refresh | 1-2 weeks
Phase 2 | 4-5 weeks
Zoning
Kimley Horn
Flash Zoning Report | 1 week
Full Zoning Report | 2 weeks
Robinson & Cole
Flash Zoning Report | 1 week (3-5 business days)
Full Zoning Report | 2 weeks (10 business days)
Test Fit
Langan
Test Fit | 1 week
Kimley Horn
Test Fit | 2 weeks

## BU Vendor Preference
SSD Vendor Preference
Flash Traffic | Kimley Horn
Flash Zoning | Robinson & Cole
TIA | Kimley Horn
Phase 1/2 | Langan/Geosyntec
Noise (Short & Long Form) | Kimley Horn
Full Zoning | Robinson & Cole
Title Commitment | Chicago Title
NACF Vendor Preference
Flash Traffic | Langan
Flash Zoning | Robinson & Cole
TIA | Langan
Phase 1/2 | Langan
Noise (Short & Long Form) | Kimley Horn
Full Zoning | Robinson & Cole
Title Commitment | Chicago Title