## Main Sheet
Metro | Site Code | Pin | Sub Metro | Recommendation | Alignment | Action and Owner
Houston | ZHS2 | Meyerland |  | Delay to 2027 | 2027
Houston | ZHS7 | Montrose |  | Delay to 2027 | 2027
Houston | ZHS8 | Uptown Houston |  | Delay to 2027 | 2027
Nashville | ZTN5 | Green Hills |  | Delay to 2027 | 2027
New Orleans | ZLA5 | CBD |  | Delay to 2027 | 2027
Philly | ZPL2 | Collingswood | NJ | Delay to 2027 | 2027
Phoenix | ZPX6 | Tempe |  | Delay to 2027 | 2027
Phoenix | ZPH1 | Deer Valley |  | Delay to 2027 | 2027
Phoenix | ZPX9 | Paradise Valley |  | Delay to 2027 | 2027
Seattle | ZBL2 | DT Bellevue-2 | Seattle | Delay to 2027 | 2027
Seattle | ZST4 | Ballard | Seattle | Delay to 2027 | 2027
Atlanta |  | Buckhead |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Atlanta | ZAT5 | Decatur |  | Launch in 2026 | 2026 Priority 1
Atlanta |  | Grant Park |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Atlanta | ZAT3 | Midtown Atlanta |  | Launched | 2026 Priority 1
Atlanta | ZAT7 | Smyrna |  | Launched | 2026 Priority 1
Austin | ZAS5 | Brentwood Austin |  | Launch in 2026 | 2026 Priority 1
Austin | ZAS7 | Travis Heights |  | Launch in 2026 | 2026 Priority 1
Austin | ZAS6 | Domain |  | Launched | 2026 Priority 1
Boston |  | Watertown |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston | ZBO4 | Jamaica Plain |  | Launch in 2026 | 2026 Priority 1
Boston |  | Somerville |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston |  | Quincy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston | ZBO5/ZBS3 | South Boston |  | Launch in 2026 | 2026 Priority 1
Boston |  | Everett |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Cincinnati | ZCL1 | DT Cincinnati |  | Launch in 2026 | 2026 Priority 1
Cleveland | ZCL2 | University Heights |  | Launch in 2026 | 2026 Priority 1
Columbus | ZCM2 | German Village |  | Launch in 2026 | 2026 Priority 1
Charlotte |  | Uptown Charlotte |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Chicago | ZCG7 | Evanston |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCH7 | Portage Park |  | Launch in 2026 | 2026 Priority 1
Chicago | ZLD1 | Kildeer |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCG6 | Elmwood Park |  | Launch in 2026 | 2026 Priority 1
Chicago | ZIL2 | West Loop |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCG1 | South Loop |  | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Columbia | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC2 | Arlington | VA | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Towson | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | Alexandria | VA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | North Bethesda | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC5 | Near Northeast | DC | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Silver Spring | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Dallas |  | Plano |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Dallas | ZDL1 | Las Colinas |  | Launch in 2026 | 2026 Priority 1
Dallas | ZDL3 | Fairmount |  | Launched | 2026 Priority 1
Dallas | ZDL4 | Cultural District |  | Launched | 2026 Priority 1
Dallas | ZDL7 | Lower Greenville |  | Launched | 2026 Priority 1
Dallas | ZDL8 | Uptown Dallas |  | Launched | 2026 Priority 1
Dallas |  | Legacy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | Columbia Heights | DC | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC4 | Tysons | VA | Launch in 2026 | 2026 Priority 1
Pittsburgh |  | Shadyside |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Denver | ZCO2 | Cherry Creek |  | Launch in 2026 | 2026 Priority 1
Denver | ZDE7 | Platt Park |  | Launch in 2026 | 2026 Priority 1
Denver | ZDV1 | Capitol Hill |  | Launch in 2026 | 2026 Priority 1
Detroit | ZDT2 | Ann Arbor |  | Launch in 2026 | 2026 Priority 1
Detroit | ZDT6 | Royal Oak |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS6 | West University Place |  | Launched | 2026 Priority 1
Houston | ZHT3 | Memorial |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS4 | Spring Branch |  | Launch in 2026 | 2026 Priority 1
Houston | ZHO5 | Cypress Houston |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS9 | Woodlands |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS1 | DT Houston |  | Launched | 2026 Priority 1
Indianapolis | ZIN1 | Meridian-Kessler |  | Launch in 2026 | 2026 Priority 1
Kansas City |  | Country Club Plaza |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Las Vegas | ZLV1 | Centennial Hills |  | Launch in 2026 | 2026 Priority 1
Las Vegas | ZLV2 | South Fork |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLG9 | Aliso Viejo |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS6 | Culver City |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Cypress |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLS9 | DT Los Angeles |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS1 | Glendale |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Orange |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles |  | Irvine |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles |  | Pasadena |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLG6 | Long Beach |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS3 | Manhattan Beach |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | North Hollywood |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLX4 | Hollywood LA |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Huntington Beach |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLG1 | Santa Monica |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Sherman Oaks |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLS4 | Woodland Hills |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLX1 | Lomita |  | Launch in 2026 | 2026 Priority 1
Miami |  | Ft Lauderdale |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Miami | ZMI2 | Coral Gables |  | Launch in 2026 | 2026 Priority 1
Miami | ZMA9 | Edgewater |  | Launch in 2026 | 2026 Priority 1
Miami |  | Boca Raton |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Miami | ZFL6 | Hollywood Miami |  | Launch in 2026 | 2026 Priority 1
Miami | ZMA5 | North Miami |  | Launch in 2026 | 2026 Priority 1
Miami | ZPB1 | West Palm Beach |  | Launch in 2026 | 2026 Priority 1
Milwaukee | ZMW1 | DT Milwaukee |  | Launch in 2026 | 2026 Priority 1
Minneapolis |  | Summit Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Minneapolis | ZMS3 | Uptown Minneapolis |  | Launch in 2026 | 2026 Priority 1
Nashville | ZTN2 | DT Nashville |  | Launch in 2026 | 2026 Priority 1
Norfolk |  | Virginia Beach Oceanfront |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN8 | Forest Hills | Queens | Launch in 2026 | 2026 Priority 1
NYC |  | DT Brooklyn | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | Summit | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZJF3 | Greenpoint | Brooklyn | Launch in 2026 | 2026 Priority 1
NYC | ZJF7 | Murray Hill | Manhattan | Launch in 2026 | 2026 Priority 1
NYC |  | Bay Ridge | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZBX1 | White Plains | Westchester County | Launch in 2026 | 2026 Priority 1
NYC | ZJF6 | DT New Haven | CT | Launch in 2026 | 2026 Priority 1
NYC |  | Hoboken | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | DT Stamford | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | SoNo | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYK1 | Fordham | Bronx | Launch in 2026 | 2026 Priority 1
NYC | ZBK8 | Bushwick | Brooklyn | Launch in 2026 | 2026 Priority 1
NYC | ZCT2 | DT Hartford | CT | Launch in 2026 | 2026 Priority 1
NYC |  | Chelsea | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN5 | DT Manhattan | Manhattan | Launch in 2026 | 2026 Priority 1
NYC | ZJF8 | Upper East Side | Manhattan | Launch in 2026 | 2026 Priority 1
NYC |  | Upper West Side | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN6 | Harlem | Manhattan | Launch in 2026 | 2026 Priority 1
NYC | ZJC1 | Jersey City | NJ | Launch in 2026 | 2026 Priority 1
NYC | ZYY7 | Mount Vernon | Westchester County | Launch in 2026 | 2026 Priority 1
Oklahoma City |  | Nichols Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Winter Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Baldwin Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Dr Phillips |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Philly | ZPL4 | Fishtown | PA | Launched | 2026 Priority 1
Philly | ZPL3 | Oxford Circle | PA | Launched | 2026 Priority 1
Philly | ZPL5 | Queen Village | PA | Launched | 2026 Priority 1
Philly |  | Manayunk | PA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Phoenix | ZPX3 | Biltmore |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPH6 | Chandler |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPH3 | DT Phoenix |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPX8 | Kierland |  | Launched | 2026 Priority 1
Phoenix |  | Palm Valley |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Phoenix | ZPX5 | Scottsdale |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD8 | Hawthorne |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD4 | Pearl District |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD3 | Tigard |  | Launch in 2026 | 2026 Priority 1
Providence | ZRI1 | DT Providence |  | Launch in 2026 | 2026 Priority 1
Raleigh |  | DT Raleigh |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Raleigh | ZRL3 | Durham |  | Launch in 2026 | 2026 Priority 1
Sacramento | ZSM3 | Roseville |  | Launch in 2026 | 2026 Priority 1
Sacramento |  | Midtown Sacramento |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Salt Lake City | ZUT5 | Sugar House |  | Launch in 2026 | 2026 Priority 1
Salt Lake City | ZUT6 | Draper |  | Launch in 2026 | 2026 Priority 1
San Antonio | ZSA2 | DT San Antonio |  | Launch in 2026 | 2026 Priority 1
San Diego |  | DT San Diego |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Diego |  | La Jolla |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Diego |  | Carlsbad |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco | ZFR1 | Fremont | East Bay | Launch in 2026 | 2026 Priority 1
San Francisco | ZSN1 | DT San Jose | South Bay | Launch in 2026 | 2026 Priority 1
San Francisco | ZFA9 | Dublin | Tri-Valley | Launch in 2026 | 2026 Priority 1
San Francisco |  | Oakland | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Daly City | SF/Peninsula | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Sunnyvale | South Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Walnut Creek | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco | ZMT1 | San Mateo | Peninsula | Launch in 2026 | 2026 Priority 1
San Francisco |  | San Rafael | Marin County | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Seattle | ZBL1 | DT Bellevue-1 | Seattle | Launched | 2026 Priority 1
Seattle | ZST8 | Northgate | Seattle | Launched | 2026 Priority 1
Seattle | ZST7 | South Lake Union | Seattle | Launched | 2026 Priority 1
Seattle | ZST3 | University District | Seattle | Launched | 2026 Priority 1
Seattle |  | Stadium District | Tacoma | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Seattle |  | Beacon Hill | Seattle | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
St Louis | ZLI1 | DT Clayton |  | Launch in 2026 | 2026 Priority 1
Tampa | ZTP1 | DT Tampa |  | Launch in 2026 | 2026 Priority 1
Tampa | ZTP2 | St Petersburg |  | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Canton | MD | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
Indianapolis | ZIN3 | Carmel |  | Launch in 2026 | 2026 Priority 2
Kansas City | ZMO3 | DT Kansas City |  | Launch in 2026 | 2026 Priority 2
Minneapolis | ZMP1 | Shelard Park |  | Launch in 2026 | 2026 Priority 2
NYC | ZJF5 | Rockville Centre | Long Island | Launch in 2026 | 2026 priority 2
NYC |  | Massapequa | Long Island | Launch in 2026 | 2026 priority 2 | PIN yet to be selected, Global Realty
NYC | ZBK2 | Mineola | Long Island | Launch in 2026 | 2026 priority 2
NYC | ZJR2 | Newark | NJ | Launch in 2026 | 2026 priority 2
NYC | ZJR1 | Fort Lee | NJ | Launch in 2026 | 2026 priority 2
NYC | ZJR5 | Montclair | NJ | Launch in 2026 | 2026 priority 2
Salt Lake City | ZUT3 | Orem |  | Launch in 2026 | 2026 Priority 2
San Antonio |  | Stone Oak |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
San Diego | ZSD7 | Escondido |  | Launch in 2026 | 2026 Priority 2
San Diego |  | Otay Ranch |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
San Francisco |  | Campbell | South Bay | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
St Louis |  | DT St Louis |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
Columbus | ZCM3 | Short North |  | Back up | Back up for ZCM2
Denver | ZDN1 | Lower Downtown |  | Launch in 2026 (choose between Capitol Hill and Lower Downtown) | Back up for ZDV1
Detroit | ZDT3 | Birmingham |  | ZDT3 is 13 min away from Royal Oak, continue to pursue as back up | Back up for ZDT6
Milwaukee | ZMW2 | Shorewood |  | Continue to pursue 3866 N Fratney St, Milwaukee, WI 53212 as a back up to DT, 10 min away | Back up for ZMW1
NYC | ZBX5 | Parkchester | Bronx | Continue to pursue as back up | Back up
NYC | ZBK3 | Midwood | Brooklyn | Continue to pursue as back up | Back up
NYC | ZJF9 | Clinton Hill | Brooklyn | Continue to pursue as back up | Back up
NYC | ZYN7 | Park Slope | Brooklyn | Continue to pursue as back up | Back up
NYC | ZBK7 | Astoria | Queens | Continue to pursue as back up | Back up
NYC | ZYN4 | Lindenwood | Queens | Continue to pursue as back up | Back up
Philly | ZPL9 | Conshohocken | PA | Back up | Back up ¦ Evaluating WFM co-lo as primary site
San Francisco | ZFA6 | Burlingame | Peninsula | Back up for ZMT1 ¦ ZMT1 Total CAPEX verification required before deciding on ZFA2 and ZFA6 | Back up
San Francisco | ZFA2 | Redwood City | Peninsula | Back up for ZMT1 ¦ ZMT1 Total CAPEX verification required before deciding on ZFA2 and ZFA6 | Back up
Tampa | ZTP4 | South Tampa |  | Remove from topology plan, continue to pursue as a backup for DT Tampa | Backup for ZTP1
Atlanta |  | Brookhaven |  | Remove from POR | Remove from POR | Cancel pin survey
Atlanta |  | Sandy Springs |  | Remove from POR | Remove from POR | Cancel pin survey
Austin |  | Rollingwood |  | Remove from POR | Remove from POR | Cancel pin survey
Austin |  | West University |  | Remove from POR | Remove from POR | Cancel pin survey
Birmingham |  | DT Birmingham |  | Remove from POR | Remove from POR | Cancel pin survey
Birmingham |  | Homewood |  | Remove from POR | Remove from POR | Cancel pin survey
Boise | ZID1 | DT Boise |  | Remove from POR | Remove from POR | Cancel, L&E
Boise |  | Meridian - North |  | Remove from POR | Remove from POR | Cancel pin survey
Boise |  | Meridian - South |  | Remove from POR | Remove from POR | Cancel pin survey
Buffalo | ZBU1 | Allentown |  | Remove from POR | Remove from POR | Cancel, L&E
Charleston |  | Mount Pleasant |  | Remove from POR | Remove from POR | Cancel pin survey
Charlotte |  | NoDa |  | Remove from POR | Remove from POR | Cancel pin survey
Charlotte |  | South Park |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Bucktown |  | Launch in 2026 | Remove from POR | Cancel pin survey
Chicago |  | Lake View |  | Launch in 2026 | Remove from POR | Cancel pin survey
Chicago |  | Arlington Heights |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Des Plaines |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Edgewater |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Edison Park |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Elmhurst |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Garfield Ridge |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Hinsdale |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Hyde Park Chicago |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Near North Side |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Oak Lawn |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Oak Park |  | Remove from POR | Remove from POR | Cancel pin survey
Chicago |  | Winnetka |  | Remove from POR | Remove from POR | Cancel pin survey
Dallas | ZDA5 | Addison |  | Remove from POR | Remove from POR | Cancel, L&E
Dallas |  | Kessler |  | Remove from POR | Remove from POR | Cancel pin survey
Dallas |  | North Dallas |  | Remove from POR | Remove from POR | Cancel pin survey
Dallas |  | University Park |  | Remove from POR | Remove from POR | Cancel pin survey
Boston |  | Allston |  | Remove from POR | Remove from POR | Cancel pin survey
Boston |  | Back Bay |  | Remove from POR | Remove from POR | Cancel pin survey
Boston |  | Cambridge |  | Remove from POR | Remove from POR | Cancel pin survey
Boston |  | Dorchester |  | Remove from POR | Remove from POR | Cancel pin survey
Cincinnati |  | Hyde Park Cincinnati |  | Remove from POR | Remove from POR | Cancel pin survey
Cleveland |  | DT Cleveland |  | Remove from POR | Remove from POR | Cancel pin survey
Cleveland | ZCL3 | Lakewood |  | Remove from POR | Remove from POR | Cancel, L&E
Columbus |  | Upper Arlington |  | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Bethesda | MD | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | College Park | MD | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Crown | MD | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | DT Annapolis | MD | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Falls Church | VA | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Hampden | MD | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Logan Circle | DC | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Riverside | MD | Remove from POR | Remove from POR | Cancel pin survey
Denver |  | Central Park |  | Remove from POR | Remove from POR | Cancel pin survey
Denver |  | Hampden South |  | Remove from POR | Remove from POR | Cancel pin survey
Denver |  | Lakewood Denver |  | Remove from POR | Remove from POR | Cancel pin survey
Denver |  | Northwest Denver |  | Remove from POR | Remove from POR | Cancel pin survey
Denver |  | Highland Ranch |  | Remove from POR | Remove from POR | Cancel pin survey
Des Moines |  | DT Des Moines |  | Remove from POR | Remove from POR | Cancel pin survey
Des Moines |  | West Des Moines |  | Remove from POR | Remove from POR | Cancel pin survey
Detroit | ZDT5 | DT Detroit |  | Remove from POR | Remove from POR | Cancel, L&E
Detroit | ZDT4 | Grosse Pointe |  | Remove from POR | Remove from POR | Cancel, L&E
Hartford |  | DT Hartford |  | Remove from POR | Remove from POR | Cancel pin survey
Hartford |  | West Hartford |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Houston Heights |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Clear Lake |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Jersey Village |  | Remove from POR | Remove from POR | Cancel pin survey
Houston | ZHO6 | Katy |  | Remove from POR | Remove from POR | Cancel, L&E
Houston |  | Louetta |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Northside |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Pearland |  | Remove from POR | Remove from POR | Cancel pin survey
Houston |  | Sugar Land |  | Remove from POR | Remove from POR | Cancel pin survey
Indianapolis |  | DT Indianapolis |  | Remove from POR | Remove from POR | Cancel pin survey
Indianapolis |  | Fishers |  | Remove from POR | Remove from POR | Cancel pin survey
Jacksonville |  | Jacksonville Beach |  | Remove from POR | Remove from POR | Cancel pin survey
Jacksonville |  | River Side |  | Remove from POR | Remove from POR | Cancel pin survey
Kansas City |  | Armour Fields |  | Remove from POR | Remove from POR | Cancel pin survey
Kansas City | ZKC1 | North Kansas City |  | Remove from POR | Remove from POR | Cancel, L&E
Las Vegas |  | Summerlin |  | Remove from POR | Remove from POR | Cancel pin survey
Las Vegas |  | UNLV |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Carson |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Anaheim |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Bellflower |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles | ZLG8 | Brentwood Los Angeles |  | Remove from POR | Remove from POR | Cancel, L&E
Los Angeles |  | Burbank |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Corona |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Dana Point |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Downey |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Encino |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Fontana |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles | ZLX2 | Hawthorne Los Angeles |  | Remove from POR | Remove from POR | Cancel, L&E
Los Angeles |  | Hermosa Beach |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Highland Park |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Huntington Beach North |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Koreatown |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Newport Beach |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Playa Vista |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | San Clemente |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Stonegate |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | UCLA |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | West Hollywood |  | Remove from POR | Remove from POR | Cancel pin survey
Los Angeles |  | Yorba Linda |  | Remove from POR | Remove from POR | Cancel pin survey
Louisville |  | Cherokee Triangle |  | Remove from POR | Remove from POR | Cancel pin survey
Louisville | ZKY3 | St Matthews |  | Remove from POR | Remove from POR | Cancel, L&E
Memphis |  | Midtown Memphis |  | Remove from POR | Remove from POR | Cancel pin survey
Miami | ZMI6 | Pembroke Pines |  | Remove from POR | Remove from POR | Cancel, L&E
Miami |  | Aventura |  | Remove from POR | Remove from POR | Cancel pin survey
Miami |  | Brickell |  | Remove from POR | Remove from POR | Cancel pin survey
Miami |  | Doral |  | Remove from POR | Remove from POR | Cancel pin survey
Miami |  | Kendall |  | Remove from POR | Remove from POR | Cancel pin survey
Miami | ZMI5 | Miami Lakes |  | Remove from POR | Remove from POR | Cancel, L&E
Miami |  | Pompano Beach |  | Remove from POR | Remove from POR | Cancel pin survey
Miami |  | South Beach |  | Remove from POR | Remove from POR | Cancel pin survey
Miami |  | Tamiami |  | Remove from POR | Remove from POR | Cancel pin survey
Milwaukee |  | Wauwatosa |  | Remove from POR | Remove from POR | Cancel pin survey
Minneapolis |  | DT Minneapolis |  | Remove from POR | Remove from POR | Cancel pin survey
Minneapolis |  | Maple Grove |  | Remove from POR | Remove from POR | Cancel pin survey
Nashville | ZTN4 | East Nashville |  | Remove from POR | Remove from POR | Cancel, L&E
Nashville |  | Wedgewood Houston |  | Remove from POR | Remove from POR | Cancel pin survey
New Orleans |  | Uptown New Orleans |  | Remove from POR | Remove from POR | Cancel pin survey
Norfolk |  | Ghent |  | Remove from POR | Remove from POR | Cancel pin survey
Norfolk | ZVA4 | Newport News |  | Remove from POR | Remove from POR | Cancel, L&E
Norfolk |  | VB Town Center |  | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Concourse | Bronx | Remove from POR | Remove from POR | Cancel Pin Survey
NYC |  | Jamaica | Queens | Remove from POR | Remove from POR | Cancel Pin Survey
NYC |  | Riverdale | Bronx | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Flatbush | Brooklyn | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | West Hartford | CT | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Plainview | Long Island | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Glen Cove | Long Island | Remove from POR | Remove from POR | Cancel pin survey
NYC | ZBK9 | Huntington | Long Island | Remove from POR | Remove from POR | Cancel, L&E
NYC |  | Great Neck | Long Island | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Hackensack | NJ | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | East Rutherford | NJ | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Woodland Park | NJ | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Jackson Heights | Queens | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Rochdale | Queens | Remove from POR | Remove from POR | Cancel pin survey
NYC |  | Flushing | Queens | Remove from POR | Remove from POR
NYC |  | Yonkers | Westchester County | Remove from POR | Remove from POR | Cancel pin survey
NYC | ZJF4 | Port Chester | Westchester County | Remove from POR | Remove from POR | Cancel, L&E
NYC |  | Tarrytown | Westchester County | Remove from POR | Remove from POR | Cancel pin survey
NYC | ZBX4 | New Rochelle | Westchester County | Remove from POR | Remove from POR | Cancel, L&E
Oklahoma City |  | DT Oklahoma City |  | Remove from POR | Remove from POR | Cancel pin survey
Oklahoma City | ZOK6 | Moore |  | Remove from POR | Remove from POR | Cancel, L&E
Oklahoma City | ZOK2 | NW OKC |  | Remove from POR | Remove from POR | Cancel, L&E
Orlando |  | DT Orlando |  | Remove from POR | Remove from POR | Cancel pin survey
Orlando |  | Horizon West |  | Remove from POR | Remove from POR | Cancel pin survey
Orlando |  | Lake Nona |  | Remove from POR | Remove from POR | Cancel pin survey
Orlando |  | MetroWest |  | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Trolley Square | DE | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | University City | PA | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Pike Creek | DE | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Haddonfield | NJ | Remove from POR | Remove from POR | Cancel pin survey
Philly | ZPA2 | Maple Shade | NJ | Remove from POR | Remove from POR | Cancel, L&E
Philly |  | Ardmore | PA | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Mt Airy | PA | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Rittenhouse Square | PA | Remove from POR | Remove from POR | Cancel pin survey
Philly |  | Newark Philadelphia | DE | Remove from POR | Remove from POR
Phoenix |  | Arrowhead |  | Remove from POR | Remove from POR | Cancel pin survey
Phoenix |  | Santan Village |  | Remove from POR | Remove from POR | Cancel pin survey
Pittsburgh |  | Dormont |  | Remove from POR | Remove from POR | Cancel pin survey
Pittsburgh |  | DT Pittsburgh |  | Remove from POR | Remove from POR | Cancel pin survey
DC - Baltimore |  | Alexandria West | VA | Remove from POR | Remove from POR | Cancel pin survey
Portland |  | Boise |  | Remove from POR | Remove from POR | Cancel pin survey
Portland | ZPD6 | Lake Oswego |  | Remove from POR | Remove from POR | Cancel, L&E
Portland | ZPD2 | Tanasbourne |  | Remove from POR | Remove from POR | Cancel, L&E
Raleigh |  | Brier Creek |  | Remove from POR | Remove from POR | Cancel pin survey
Raleigh |  | Cary |  | Remove from POR | Remove from POR | Cancel pin survey
Raleigh |  | North Hills |  | Remove from POR | Remove from POR | Cancel pin survey
Richmond |  | Shockoe Bottom |  | Remove from POR | Remove from POR | Cancel pin survey
Richmond |  | The Fan |  | Remove from POR | Remove from POR | Cancel pin survey
Sacramento | ZSM1 | Antelope |  | Remove from POR | Remove from POR | Cancel, L&E
Sacramento |  | Elk Grove |  | Remove from POR | Remove from POR | Cancel pin survey
Sacramento | ZSM5 | Fair Oaks |  | Remove from POR | Remove from POR | Cancel, L&E
Sacramento | ZSM2 | Natomas |  | Remove from POR | Remove from POR | Cancel, L&E
Sacramento | ZSM4 | Arden-Arcade |  | Remove from POR | Remove from POR | Cancel, L&E
Salt Lake City |  | Cottonwood Heights |  | Remove from POR | Remove from POR | Cancel pin survey
Salt Lake City |  | Daybreak |  | Remove from POR | Remove from POR | Cancel pin survey
Salt Lake City |  | DT Salt Lake City |  | Remove from POR | Remove from POR | Cancel pin survey
Salt Lake City |  | Lehi |  | Remove from POR | Remove from POR | Cancel pin survey
Salt Lake City |  | Taylorsville |  | Remove from POR | Remove from POR | Cancel pin survey
San Antonio |  | Alamo Heights |  | Remove from POR | Remove from POR | Cancel pin survey
San Diego |  | North Park |  | Remove from POR | Remove from POR | Cancel pin survey
San Diego |  | Del Mar |  | Remove from POR | Remove from POR | Cancel pin survey
San Diego |  | Encinitas |  | Remove from POR | Remove from POR | Cancel pin survey
San Diego |  | Hillcrest |  | Remove from POR | Remove from POR | Cancel pin survey
San Diego | ZSD8 | Mira Mesa |  | Remove from POR | Remove from POR | Cancel, L&E
San Diego |  | Pacific Beach |  | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Berkeley | East Bay | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Hayward | East Bay | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Richmond | East Bay | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Mill Valley | Marin County | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Palo Alto | Peninsula | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Central Richmond | SF | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Hayes Valley | SF | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Noe Valley | SF | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Pacific Heights | SF | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Rincon Hill | SF | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Cupertino | South Bay | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Santana Row | South Bay | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | San Ramon | Tri-Valley | Remove from POR | Remove from POR | Cancel pin survey
San Francisco |  | Alameda | East Bay | Remove from POR | Remove from POR | Cancel pin survey
Sarasota |  | DT Sarasota |  | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | West Seattle | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | Bothell | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | Issaquah | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | Kirkland | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | New Castle | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle |  | Redmond | Seattle | Remove from POR | Remove from POR | Cancel pin survey
Seattle | ZSL3 | Shoreline | Seattle | Remove from POR | Remove from POR | Cancel, L&E
Seattle |  | University Place | Tacoma | Remove from POR | Remove from POR | Cancel pin survey
St Louis |  | Central West End |  | Remove from POR | Remove from POR | Cancel pin survey
Tucson |  | U of A |  | Remove from POR | Remove from POR | Cancel pin survey
Buffalo | ZBU2 | North Buffalo |  | TBD | TBD
Charleston | ZSC1 | DT Charleston |  | TBD | TBD
San Francisco | ZXC4 | Milpitas | South Bay | Topology checking if required for 2027 | TBD
Tampa | ZTP3 | DT Sarasota |  | TBD | TBD

## 2026 Active Pins (P1 & P2)
Metro | Site Code | Pin | ID | Sub Metro | Recommendation | Alignment | Action and Owner
Atlanta |  | Buckhead | AtlantaBuckhead |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Atlanta | ZAT5 | Decatur | AtlantaDecatur |  | Launch in 2026 | 2026 Priority 1
Atlanta |  | Grant Park | AtlantaGrant Park |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Atlanta | ZAT3 | Midtown Atlanta | AtlantaMidtown Atlanta |  | Launched | 2026 Priority 1
Atlanta | ZAT7 | Smyrna | AtlantaSmyrna |  | Launched | 2026 Priority 1
Austin | ZAS5 | Brentwood Austin | AustinBrentwood Austin |  | Launch in 2026 | 2026 Priority 1
Austin | ZAS7 | Travis Heights | AustinTravis Heights |  | Launch in 2026 | 2026 Priority 1
Austin | ZAS6 | Domain | AustinDomain |  | Launched | 2026 Priority 1
Boston |  | Watertown | BostonWatertown |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston | ZBO4 | Jamaica Plain | BostonJamaica Plain |  | Launch in 2026 | 2026 Priority 1
Boston |  | Somerville | BostonSomerville |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston |  | Quincy | BostonQuincy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Boston | ZBO5/ZBS3 | South Boston | BostonSouth Boston |  | Launch in 2026 | 2026 Priority 1
Boston |  | Everett | BostonEverett |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Cincinnati | ZCL1 | DT Cincinnati | CincinnatiDT Cincinnati |  | Launch in 2026 | 2026 Priority 1
Cleveland | ZCL2 | University Heights | ClevelandUniversity Heights |  | Launch in 2026 | 2026 Priority 1
Columbus | ZCM2 | German Village | ColumbusGerman Village |  | Launch in 2026 | 2026 Priority 1
Charlotte |  | Uptown Charlotte | CharlotteUptown Charlotte |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Chicago | ZCG7 | Evanston | ChicagoEvanston |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCH7 | Portage Park | ChicagoPortage Park |  | Launch in 2026 | 2026 Priority 1
Chicago | ZLD1 | Kildeer | ChicagoKildeer |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCG6 | Elmwood Park | ChicagoElmwood Park |  | Launch in 2026 | 2026 Priority 1
Chicago | ZIL2 | West Loop | ChicagoWest Loop |  | Launch in 2026 | 2026 Priority 1
Chicago | ZCG1 | South Loop | ChicagoSouth Loop |  | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Columbia | DC - BaltimoreColumbia | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC2 | Arlington | DC - BaltimoreArlington | VA | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Towson | DC - BaltimoreTowson | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | Alexandria | DC - BaltimoreAlexandria | VA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | North Bethesda | DC - BaltimoreNorth Bethesda | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC5 | Near Northeast | DC - BaltimoreNear Northeast | DC | Launch in 2026 | 2026 Priority 1
DC - Baltimore |  | Canton | DC - BaltimoreCanton | MD | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
DC - Baltimore |  | Silver Spring | DC - BaltimoreSilver Spring | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Dallas |  | Plano | DallasPlano |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Dallas | ZDL1 | Las Colinas | DallasLas Colinas |  | Launch in 2026 | 2026 Priority 1
Dallas | ZDL3 | Fairmount | DallasFairmount |  | Launched | 2026 Priority 1
Dallas | ZDL4 | Cultural District | DallasCultural District |  | Launched | 2026 Priority 1
Dallas | ZDL7 | Lower Greenville | DallasLower Greenville |  | Launched | 2026 Priority 1
Dallas | ZDL8 | Uptown Dallas | DallasUptown Dallas |  | Launched | 2026 Priority 1
Dallas |  | Legacy | DallasLegacy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore |  | Columbia Heights | DC - BaltimoreColumbia Heights | DC | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
DC - Baltimore | ZDC4 | Tysons | DC - BaltimoreTysons | VA | Launch in 2026 | 2026 Priority 1
Pittsburgh |  | Shadyside | PittsburghShadyside |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Denver | ZCO2 | Cherry Creek | DenverCherry Creek |  | Launch in 2026 | 2026 Priority 1
Denver | ZDE7 | Platt Park | DenverPlatt Park |  | Launch in 2026 | 2026 Priority 1
Denver | ZDV1 | Capitol Hill | DenverCapitol Hill |  | Launch in 2026 | 2026 Priority 1
Detroit | ZDT2 | Ann Arbor | DetroitAnn Arbor |  | Launch in 2026 | 2026 Priority 1
Detroit | ZDT6 | Royal Oak | DetroitRoyal Oak |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS6 | West University Place | HoustonWest University Place |  | Launched | 2026 Priority 1
Houston | ZHT3 | Memorial | HoustonMemorial |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS4 | Spring Branch | HoustonSpring Branch |  | Launch in 2026 | 2026 Priority 1
Houston | ZHO5 | Cypress Houston | HoustonCypress Houston |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS9 | Woodlands | HoustonWoodlands |  | Launch in 2026 | 2026 Priority 1
Houston | ZHS1 | DT Houston | HoustonDT Houston |  | Launched | 2026 Priority 1
Indianapolis | ZIN3 | Carmel | IndianapolisCarmel |  | Launch in 2026 | 2026 Priority 2
Indianapolis | ZIN1 | Meridian-Kessler | IndianapolisMeridian-Kessler |  | Launch in 2026 | 2026 Priority 1
Kansas City |  | Country Club Plaza | Kansas CityCountry Club Plaza |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Kansas City | ZMO3 | DT Kansas City | Kansas CityDT Kansas City |  | Launch in 2026 | 2026 Priority 2
Las Vegas | ZLV1 | Centennial Hills | Las VegasCentennial Hills |  | Launch in 2026 | 2026 Priority 1
Las Vegas | ZLV2 | South Fork | Las VegasSouth Fork |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLG9 | Aliso Viejo | Los AngelesAliso Viejo |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS6 | Culver City | Los AngelesCulver City |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Cypress | Los AngelesCypress |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLS9 | DT Los Angeles | Los AngelesDT Los Angeles |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS1 | Glendale | Los AngelesGlendale |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Orange | Los AngelesOrange |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles |  | Irvine | Los AngelesIrvine |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles |  | Pasadena | Los AngelesPasadena |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLG6 | Long Beach | Los AngelesLong Beach |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLS3 | Manhattan Beach | Los AngelesManhattan Beach |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | North Hollywood | Los AngelesNorth Hollywood |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLX4 | Hollywood LA | Los AngelesHollywood LA |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Huntington Beach | Los AngelesHuntington Beach |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLG1 | Santa Monica | Los AngelesSanta Monica |  | Launch in 2026 | 2026 Priority 1
Los Angeles |  | Sherman Oaks | Los AngelesSherman Oaks |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Los Angeles | ZLS4 | Woodland Hills | Los AngelesWoodland Hills |  | Launch in 2026 | 2026 Priority 1
Los Angeles | ZLX1 | Lomita | Los AngelesLomita |  | Launch in 2026 | 2026 Priority 1
Miami |  | Ft Lauderdale | MiamiFt Lauderdale |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Miami | ZMI2 | Coral Gables | MiamiCoral Gables |  | Launch in 2026 | 2026 Priority 1
Miami | ZMA9 | Edgewater | MiamiEdgewater |  | Launch in 2026 | 2026 Priority 1
Miami |  | Boca Raton | MiamiBoca Raton |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Miami | ZFL6 | Hollywood Miami | MiamiHollywood Miami |  | Launch in 2026 | 2026 Priority 1
Miami | ZMA5 | North Miami | MiamiNorth Miami |  | Launch in 2026 | 2026 Priority 1
Miami | ZPB1 | West Palm Beach | MiamiWest Palm Beach |  | Launch in 2026 | 2026 Priority 1
Milwaukee | ZMW1 | DT Milwaukee | MilwaukeeDT Milwaukee |  | Launch in 2026 | 2026 Priority 1
Minneapolis | ZMP1 | Shelard Park | MinneapolisShelard Park |  | Launch in 2026 | 2026 Priority 2
Minneapolis |  | Summit Hills | MinneapolisSummit Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Minneapolis | ZMS3 | Uptown Minneapolis | MinneapolisUptown Minneapolis |  | Launch in 2026 | 2026 Priority 1
Nashville | ZTN2 | DT Nashville | NashvilleDT Nashville |  | Launch in 2026 | 2026 Priority 1
Norfolk |  | Virginia Beach Oceanfront | NorfolkVirginia Beach Oceanfront |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN8 | Forest Hills | NYCForest Hills | Queens | Launch in 2026 | 2026 Priority 1
NYC |  | DT Brooklyn | NYCDT Brooklyn | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | Summit | NYCSummit | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZJF3 | Greenpoint | NYCGreenpoint | Brooklyn | Launch in 2026 | 2026 Priority 1
NYC | ZJF7 | Murray Hill | NYCMurray Hill | Manhattan | Launch in 2026 | 2026 Priority 1
NYC |  | Bay Ridge | NYCBay Ridge | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZBX1 | White Plains | NYCWhite Plains | Westchester County | Launch in 2026 | 2026 Priority 1
NYC | ZJF6 | DT New Haven | NYCDT New Haven | CT | Launch in 2026 | 2026 Priority 1
NYC |  | Hoboken | NYCHoboken | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | DT Stamford | NYCDT Stamford | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC |  | SoNo | NYCSoNo | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYK1 | Fordham | NYCFordham | Bronx | Launch in 2026 | 2026 Priority 1
NYC | ZBK8 | Bushwick | NYCBushwick | Brooklyn | Launch in 2026 | 2026 Priority 1
NYC | ZCT2 | DT Hartford | NYCDT Hartford | CT | Launch in 2026 | 2026 Priority 1
NYC |  | Chelsea | NYCChelsea | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN5 | DT Manhattan | NYCDT Manhattan | Manhattan | Launch in 2026 | 2026 Priority 1
NYC | ZJF8 | Upper East Side | NYCUpper East Side | Manhattan | Launch in 2026 | 2026 Priority 1
NYC |  | Upper West Side | NYCUpper West Side | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
NYC | ZYN6 | Harlem | NYCHarlem | Manhattan | Launch in 2026 | 2026 Priority 1
NYC | ZJC1 | Jersey City | NYCJersey City | NJ | Launch in 2026 | 2026 Priority 1
NYC | ZYY7 | Mount Vernon | NYCMount Vernon | Westchester County | Launch in 2026 | 2026 Priority 1
NYC | ZJF5 | Rockville Centre | NYCRockville Centre | Long Island | Launch in 2026 | 2026 priority 2
NYC |  | Massapequa | NYCMassapequa | Long Island | Launch in 2026 | 2026 priority 2 | PIN yet to be selected, Global Realty
NYC | ZBK2 | Mineola | NYCMineola | Long Island | Launch in 2026 | 2026 priority 2
NYC | ZJR2 | Newark | NYCNewark | NJ | Launch in 2026 | 2026 priority 2
NYC | ZJR1 | Fort Lee | NYCFort Lee | NJ | Launch in 2026 | 2026 priority 2
NYC | ZJR5 | Montclair | NYCMontclair | NJ | Launch in 2026 | 2026 priority 2
Oklahoma City |  | Nichols Hills | Oklahoma CityNichols Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Winter Park | OrlandoWinter Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Baldwin Park | OrlandoBaldwin Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
Orlando |  | Dr Phillips | OrlandoDr Phillips |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Philly | ZPL4 | Fishtown | PhillyFishtown | PA | Launched | 2026 Priority 1
Philly | ZPL3 | Oxford Circle | PhillyOxford Circle | PA | Launched | 2026 Priority 1
Philly | ZPL5 | Queen Village | PhillyQueen Village | PA | Launched | 2026 Priority 1
Philly |  | Manayunk | PhillyManayunk | PA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Phoenix | ZPX3 | Biltmore | PhoenixBiltmore |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPH6 | Chandler | PhoenixChandler |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPH3 | DT Phoenix | PhoenixDT Phoenix |  | Launch in 2026 | 2026 Priority 1
Phoenix | ZPX8 | Kierland | PhoenixKierland |  | Launched | 2026 Priority 1
Phoenix |  | Palm Valley | PhoenixPalm Valley |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Phoenix | ZPX5 | Scottsdale | PhoenixScottsdale |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD8 | Hawthorne | PortlandHawthorne |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD4 | Pearl District | PortlandPearl District |  | Launch in 2026 | 2026 Priority 1
Portland | ZPD3 | Tigard | PortlandTigard |  | Launch in 2026 | 2026 Priority 1
Providence | ZRI1 | DT Providence | ProvidenceDT Providence |  | Launch in 2026 | 2026 Priority 1
Raleigh |  | DT Raleigh | RaleighDT Raleigh |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Raleigh | ZRL3 | Durham | RaleighDurham |  | Launch in 2026 | 2026 Priority 1
Sacramento | ZSM3 | Roseville | SacramentoRoseville |  | Launch in 2026 | 2026 Priority 1
Sacramento |  | Midtown Sacramento | SacramentoMidtown Sacramento |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Salt Lake City | ZUT3 | Orem | Salt Lake CityOrem |  | Launch in 2026 | 2026 Priority 2
Salt Lake City | ZUT5 | Sugar House | Salt Lake CitySugar House |  | Launch in 2026 | 2026 Priority 1
Salt Lake City | ZUT6 | Draper | Salt Lake CityDraper |  | Launch in 2026 | 2026 Priority 1
San Antonio | ZSA2 | DT San Antonio | San AntonioDT San Antonio |  | Launch in 2026 | 2026 Priority 1
San Antonio |  | Stone Oak | San AntonioStone Oak |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
San Diego | ZSD7 | Escondido | San DiegoEscondido |  | Launch in 2026 | 2026 Priority 2
San Diego |  | DT San Diego | San DiegoDT San Diego |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Diego |  | La Jolla | San DiegoLa Jolla |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Diego |  | Carlsbad | San DiegoCarlsbad |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Diego |  | Otay Ranch | San DiegoOtay Ranch |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
San Francisco | ZFR1 | Fremont | San FranciscoFremont | East Bay | Launch in 2026 | 2026 Priority 1
San Francisco | ZSN1 | DT San Jose | San FranciscoDT San Jose | South Bay | Launch in 2026 | 2026 Priority 1
San Francisco | ZFA9 | Dublin | San FranciscoDublin | Tri-Valley | Launch in 2026 | 2026 Priority 1
San Francisco |  | Oakland | San FranciscoOakland | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Daly City | San FranciscoDaly City | SF/Peninsula | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Sunnyvale | San FranciscoSunnyvale | South Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Walnut Creek | San FranciscoWalnut Creek | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco | ZMT1 | San Mateo | San FranciscoSan Mateo | Peninsula | Launch in 2026 | 2026 Priority 1
San Francisco |  | San Rafael | San FranciscoSan Rafael | Marin County | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
San Francisco |  | Campbell | San FranciscoCampbell | South Bay | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
Seattle | ZBL1 | DT Bellevue-1 | SeattleDT Bellevue-1 | Seattle | Launched | 2026 Priority 1
Seattle | ZST8 | Northgate | SeattleNorthgate | Seattle | Launched | 2026 Priority 1
Seattle | ZST7 | South Lake Union | SeattleSouth Lake Union | Seattle | Launched | 2026 Priority 1
Seattle | ZST3 | University District | SeattleUniversity District | Seattle | Launched | 2026 Priority 1
Seattle |  | Stadium District | SeattleStadium District | Tacoma | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
Seattle |  | Beacon Hill | SeattleBeacon Hill | Seattle | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
St Louis | ZLI1 | DT Clayton | St LouisDT Clayton |  | Launch in 2026 | 2026 Priority 1
St Louis |  | DT St Louis | St LouisDT St Louis |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
Tampa | ZTP1 | DT Tampa | TampaDT Tampa |  | Launch in 2026 | 2026 Priority 1
Tampa | ZTP2 | St Petersburg | TampaSt Petersburg |  | Launch in 2026 | 2026 Priority 1

## Selected Sites - Cancellations
Sr No. | Metro | Site Code | Pin | Sub Metro | Recommendation | Alignment | Action and Owner
1 | Boise | ZID1 | DT Boise |  | Remove from POR | Remove from POR | Cancel, L&E
2 | Buffalo | ZBU1 | Allentown |  | Remove from POR | Remove from POR | Cancel, L&E
3 | Dallas | ZDA5 | Addison |  | Remove from POR | Remove from POR | Cancel, L&E
4 | Cleveland | ZCL3 | Lakewood |  | Remove from POR | Remove from POR | Cancel, L&E
5 | Detroit | ZDT5 | DT Detroit |  | Remove from POR | Remove from POR | Cancel, L&E
6 | Detroit | ZDT4 | Grosse Pointe |  | Remove from POR | Remove from POR | Cancel, L&E
7 | Houston | ZHO6 | Katy |  | Remove from POR | Remove from POR | Cancel, L&E
8 | Kansas City | ZKC1 | North Kansas City |  | Remove from POR | Remove from POR | Cancel, L&E
9 | Los Angeles | ZLG8 | Brentwood Los Angeles |  | Remove from POR | Remove from POR | Cancel, L&E
10 | Los Angeles | ZLX2 | Hawthorne Los Angeles |  | Remove from POR | Remove from POR | Cancel, L&E
11 | Louisville | ZKY3 | St Matthews |  | Remove from POR | Remove from POR | Cancel, L&E
12 | Miami | ZMI6 | Pembroke Pines |  | Remove from POR | Remove from POR | Cancel, L&E
13 | Miami | ZMI5 | Miami Lakes |  | Remove from POR | Remove from POR | Cancel, L&E
14 | Nashville | ZTN4 | East Nashville |  | Remove from POR | Remove from POR | Cancel, L&E
15 | Norfolk | ZVA4 | Newport News |  | Remove from POR | Remove from POR | Cancel, L&E
16 | NYC | ZBK9 | Huntington | Long Island | Remove from POR | Remove from POR | Cancel, L&E
17 | NYC | ZJF4 | Port Chester | Westchester County | Remove from POR | Remove from POR | Cancel, L&E
18 | NYC | ZBX4 | New Rochelle | Westchester County | Remove from POR | Remove from POR | Cancel, L&E
19 | Oklahoma City | ZOK6 | Moore |  | Remove from POR | Remove from POR | Cancel, L&E
20 | Oklahoma City | ZOK2 | NW OKC |  | Remove from POR | Remove from POR | Cancel, L&E
21 | Philly | ZPA2 | Maple Shade | NJ | Remove from POR | Remove from POR | Cancel, L&E
22 | Portland | ZPD6 | Lake Oswego |  | Remove from POR | Remove from POR | Cancel, L&E
23 | Portland | ZPD2 | Tanasbourne |  | Remove from POR | Remove from POR | Cancel, L&E
24 | Sacramento | ZSM1 | Antelope |  | Remove from POR | Remove from POR | Cancel, L&E
25 | Sacramento | ZSM5 | Fair Oaks |  | Remove from POR | Remove from POR | Cancel, L&E
26 | Sacramento | ZSM2 | Natomas |  | Remove from POR | Remove from POR | Cancel, L&E
27 | Sacramento | ZSM4 | Arden-Arcade |  | Remove from POR | Remove from POR | Cancel, L&E
28 | San Diego | ZSD8 | Mira Mesa |  | Remove from POR | Remove from POR | Cancel, L&E
29 | Seattle | ZSL3 | Shoreline | Seattle | Remove from POR | Remove from POR | Cancel, L&E

## Pins Pending Site Selection
Sr No | Metro | Pin | Sub Metro | Recommendation | Alignment | Action and Owner
1 | Atlanta | Buckhead |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
2 | Atlanta | Grant Park |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
3 | Boston | Watertown |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
4 | Boston | Somerville |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
5 | Boston | Quincy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
6 | Boston | Everett |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
7 | Charlotte | Uptown Charlotte |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
8 | DC - Baltimore | Columbia | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
9 | DC - Baltimore | Towson | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
10 | DC - Baltimore | Alexandria | VA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
11 | DC - Baltimore | North Bethesda | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
12 | DC - Baltimore | Canton | MD | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
13 | DC - Baltimore | Silver Spring | MD | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
14 | Dallas | Plano |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
15 | Dallas | Legacy |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
16 | DC - Baltimore | Columbia Heights | DC | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
17 | Pittsburgh | Shadyside |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
18 | Kansas City | Country Club Plaza |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
19 | Los Angeles | Cypress |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
20 | Los Angeles | Orange |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
21 | Los Angeles | Irvine |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
22 | Los Angeles | Pasadena |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
23 | Los Angeles | North Hollywood |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
24 | Los Angeles | Huntington Beach |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
25 | Los Angeles | Sherman Oaks |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
26 | Miami | Ft Lauderdale |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
27 | Miami | Boca Raton |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
28 | Minneapolis | Summit Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
29 | Norfolk | Virginia Beach Oceanfront |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
30 | NYC | DT Brooklyn | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
31 | NYC | Summit | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
32 | NYC | Bay Ridge | Brooklyn | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
33 | NYC | Hoboken | NJ | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
34 | NYC | DT Stamford | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
35 | NYC | SoNo | CT | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
36 | NYC | Chelsea | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
37 | NYC | Upper West Side | Manhattan | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
38 | NYC | Massapequa | Long Island | Launch in 2026 | 2026 priority 2 | PIN yet to be selected, Global Realty
39 | Oklahoma City | Nichols Hills |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
40 | Orlando | Winter Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
41 | Orlando | Baldwin Park |  | Launch in 2026 (choose 1 from 2) | 2026 Priority 1 | PIN yet to be selected, Global Realty
42 | Orlando | Dr Phillips |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
43 | Philly | Manayunk | PA | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
44 | Phoenix | Palm Valley |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
45 | Raleigh | DT Raleigh |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
46 | Sacramento | Midtown Sacramento |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
47 | San Antonio | Stone Oak |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
48 | San Diego | DT San Diego |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
49 | San Diego | La Jolla |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
50 | San Diego | Carlsbad |  | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
51 | San Diego | Otay Ranch |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
52 | San Francisco | Oakland | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
53 | San Francisco | Daly City | SF/Peninsula | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
54 | San Francisco | Sunnyvale | South Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
55 | San Francisco | Walnut Creek | East Bay | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
56 | San Francisco | San Rafael | Marin County | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
57 | San Francisco | Campbell | South Bay | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty
58 | Seattle | Stadium District | Tacoma | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
59 | Seattle | Beacon Hill | Seattle | Launch in 2026 | 2026 Priority 1 | PIN yet to be selected, Global Realty
60 | St Louis | DT St Louis |  | Launch in 2026 | 2026 Priority 2 | PIN yet to be selected, Global Realty

## TBD Sites
Sr No | Metro | Site Code | Pin | Recommendation | Alignment | Notes
1 | Buffalo | ZBU2 | North Buffalo | TBD | TBD | Proceed as normal
2 | Charleston | ZSC1 | DT Charleston | TBD | TBD | Proceed as normal
3 | San Francisco | ZXC4 | Milpitas | Topology checking if required for 2027 | TBD | Proceed as normal
4 | Tampa | ZTP3 | DT Sarasota | TBD | TBD | Proceed as normal

## Delay to 2027
Sr No | Metro | Site Code | Pin | Sub Metro | Recommendation | Alignment | Action and Owner
1 | Houston | ZHS2 | Meyerland |  | Delay to 2027 | 2027 | Continue as normal
2 | Houston | ZHS7 | Montrose |  | Delay to 2027 | 2027 | Continue as normal
3 | Houston | ZHS8 | Uptown Houston |  | Delay to 2027 | 2027 | Continue as normal
4 | Nashville | ZTN5 | Green Hills |  | Launch in 2027 | 2027 | Continue as normal
5 | New Orleans | ZLA5 | CBD |  | Launch in 2027 | 2027 | Continue as normal
6 | Philly | ZPL2 | Collingswood | NJ | Delay to 2027 | 2027 | Continue as normal
7 | Phoenix | ZPX6 | Tempe |  | Delay to 2027 | 2027 | Continue as normal
8 | Phoenix | ZPH1 | Deer Valley |  | Delay to 2027 | 2027 | Continue as normal
9 | Phoenix | ZPX9 | Paradise Valley |  | Delay to 2027 | 2027 | Continue as normal
10 | Seattle | ZBL2 | DT Bellevue-2 | Seattle | Delay to 2027 | 2027 | Continue as normal
11 | Seattle | ZST4 | Ballard | Seattle | Delay to 2027 | 2027 | Continue as normal

## Backups
Sr No | Metro | Site Code | Pin | Sub Metro | Recommendation | Alignment
1 | Columbus | ZCM3 | Short North |  | Back up | Back up for ZCM2
2 | Denver | ZDN1 | Lower Downtown |  | Launch in 2026 (choose between Capitol Hill and Lower Downtown) | Back up for ZDV1
3 | Detroit | ZDT3 | Birmingham |  | ZDT3 is 13 min away from Royal Oak, continue to pursue as back up | Back up for ZDT6
4 | Milwaukee | ZMW2 | Shorewood |  | Continue to pursue 3866 N Fratney St, Milwaukee, WI 53212 as a back up to DT, 10 min away | Back up for ZMW1
5 | NYC | ZBX5 | Parkchester | Bronx | Continue to pursue as back up | Back up
6 | NYC | ZBK3 | Midwood | Brooklyn | Continue to pursue as back up | Back up
7 | NYC | ZJF9 | Clinton Hill | Brooklyn | Continue to pursue as back up | Back up
8 | NYC | ZYN7 | Park Slope | Brooklyn | Continue to pursue as back up | Back up
9 | NYC | ZBK7 | Astoria | Queens | Continue to pursue as back up | Back up
10 | NYC | ZYN4 | Lindenwood | Queens | Continue to pursue as back up | Back up
11 | Philly | ZPL9 | Conshohocken | PA | Back up | Back up ¦ Evaluating WFM co-lo as primary site
12 | Tampa | ZTP4 | South Tampa |  | Remove from topology plan, continue to pursue as a backup for DT Tampa | Backup for ZTP1
13 | San Francisco | ZFA6 | Burlingame |  | Back up for ZMT1 ¦ ZMT1 Total CAPEX verification required before deciding on ZFA2 and ZFA6 | Back up
14 | San Francisco | ZFA2 | Redwood City |  | Back up for ZMT1 ¦ ZMT1 Total CAPEX verification required before deciding on ZFA2 and ZFA6 | Back up

## Pins removed from the POR
Sr No | Metro | Pin | Sub Metro | Recommendation | Alignment | Action and Owner
1 | Atlanta | Brookhaven |  | Remove from POR | Remove from POR | Cancel pin survey
2 | Atlanta | Sandy Springs |  | Remove from POR | Remove from POR | Cancel pin survey
3 | Austin | Rollingwood |  | Remove from POR | Remove from POR | Cancel pin survey
4 | Austin | West University |  | Remove from POR | Remove from POR | Cancel pin survey
5 | Birmingham | DT Birmingham |  | Remove from POR | Remove from POR | Cancel pin survey
6 | Birmingham | Homewood |  | Remove from POR | Remove from POR | Cancel pin survey
7 | Boise | Meridian - North |  | Remove from POR | Remove from POR | Cancel pin survey
8 | Boise | Meridian - South |  | Remove from POR | Remove from POR | Cancel pin survey
9 | Charleston | Mount Pleasant |  | Remove from POR | Remove from POR | Cancel pin survey
10 | Charlotte | NoDa |  | Remove from POR | Remove from POR | Cancel pin survey
11 | Charlotte | South Park |  | Remove from POR | Remove from POR | Cancel pin survey
12 | Chicago | Bucktown |  | Remove from POR | Remove from POR | Cancel pin survey
13 | Chicago | Lake View |  | Remove from POR | Remove from POR | Cancel pin survey
14 | Chicago | Arlington Heights |  | Remove from POR | Remove from POR | Cancel pin survey
15 | Chicago | Des Plaines |  | Remove from POR | Remove from POR | Cancel pin survey
16 | Chicago | Edgewater |  | Remove from POR | Remove from POR | Cancel pin survey
17 | Chicago | Edison Park |  | Remove from POR | Remove from POR | Cancel pin survey
18 | Chicago | Elmhurst |  | Remove from POR | Remove from POR | Cancel pin survey
19 | Chicago | Garfield Ridge |  | Remove from POR | Remove from POR | Cancel pin survey
20 | Chicago | Hinsdale |  | Remove from POR | Remove from POR | Cancel pin survey
21 | Chicago | Hyde Park Chicago |  | Remove from POR | Remove from POR | Cancel pin survey
22 | Chicago | Near North Side |  | Remove from POR | Remove from POR | Cancel pin survey
23 | Chicago | Oak Lawn |  | Remove from POR | Remove from POR | Cancel pin survey
24 | Chicago | Oak Park |  | Remove from POR | Remove from POR | Cancel pin survey
25 | Chicago | Winnetka |  | Remove from POR | Remove from POR | Cancel pin survey
26 | Dallas | Kessler |  | Remove from POR | Remove from POR | Cancel pin survey
27 | Dallas | North Dallas |  | Remove from POR | Remove from POR | Cancel pin survey
28 | Dallas | University Park |  | Remove from POR | Remove from POR | Cancel pin survey
29 | Boston | Allston |  | Remove from POR | Remove from POR | Cancel pin survey
30 | Boston | Back Bay |  | Remove from POR | Remove from POR | Cancel pin survey
31 | Boston | Cambridge |  | Remove from POR | Remove from POR | Cancel pin survey
32 | Boston | Dorchester |  | Remove from POR | Remove from POR | Cancel pin survey
33 | Cincinnati | Hyde Park Cincinnati |  | Remove from POR | Remove from POR | Cancel pin survey
34 | Cleveland | DT Cleveland |  | Remove from POR | Remove from POR | Cancel pin survey
35 | Columbus | Upper Arlington |  | Remove from POR | Remove from POR | Cancel pin survey
36 | DC - Baltimore | Bethesda | MD | Remove from POR | Remove from POR | Cancel pin survey
37 | DC - Baltimore | College Park | MD | Remove from POR | Remove from POR | Cancel pin survey
38 | DC - Baltimore | Crown | MD | Remove from POR | Remove from POR | Cancel pin survey
39 | DC - Baltimore | DT Annapolis | MD | Remove from POR | Remove from POR | Cancel pin survey
40 | DC - Baltimore | Falls Church | VA | Remove from POR | Remove from POR | Cancel pin survey
41 | DC - Baltimore | Hampden | MD | Remove from POR | Remove from POR | Cancel pin survey
42 | DC - Baltimore | Logan Circle | DC | Remove from POR | Remove from POR | Cancel pin survey
43 | DC - Baltimore | Riverside | MD | Remove from POR | Remove from POR | Cancel pin survey
44 | Denver | Central Park |  | Remove from POR | Remove from POR | Cancel pin survey
45 | Denver | Hampden South |  | Remove from POR | Remove from POR | Cancel pin survey
46 | Denver | Lakewood Denver |  | Remove from POR | Remove from POR | Cancel pin survey
47 | Denver | Northwest Denver |  | Remove from POR | Remove from POR | Cancel pin survey
48 | Denver | Highland Ranch |  | Remove from POR | Remove from POR | Cancel pin survey
49 | Des Moines | DT Des Moines |  | Remove from POR | Remove from POR | Cancel pin survey
50 | Des Moines | West Des Moines |  | Remove from POR | Remove from POR | Cancel pin survey
51 | Hartford | DT Hartford |  | Remove from POR | Remove from POR | Cancel pin survey
52 | Hartford | West Hartford |  | Remove from POR | Remove from POR | Cancel pin survey
53 | Houston | Houston Heights |  | Remove from POR | Remove from POR | Cancel pin survey
54 | Houston | Clear Lake |  | Remove from POR | Remove from POR | Cancel pin survey
55 | Houston | Jersey Village |  | Remove from POR | Remove from POR | Cancel pin survey
56 | Houston | Louetta |  | Remove from POR | Remove from POR | Cancel pin survey
57 | Houston | Northside |  | Remove from POR | Remove from POR | Cancel pin survey
58 | Houston | Pearland |  | Remove from POR | Remove from POR | Cancel pin survey
59 | Houston | Sugar Land |  | Remove from POR | Remove from POR | Cancel pin survey
60 | Indianapolis | DT Indianapolis |  | Remove from POR | Remove from POR | Cancel pin survey
61 | Indianapolis | Fishers |  | Remove from POR | Remove from POR | Cancel pin survey
62 | Jacksonville | Jacksonville Beach |  | Remove from POR | Remove from POR | Cancel pin survey
63 | Jacksonville | River Side |  | Remove from POR | Remove from POR | Cancel pin survey
64 | Kansas City | Armour Fields |  | Remove from POR | Remove from POR | Cancel pin survey
65 | Las Vegas | Summerlin |  | Remove from POR | Remove from POR | Cancel pin survey
66 | Las Vegas | UNLV |  | Remove from POR | Remove from POR | Cancel pin survey
67 | Los Angeles | Carson |  | Remove from POR | Remove from POR | Cancel Pin Survey
68 | Los Angeles | Anaheim |  | Remove from POR | Remove from POR | Cancel pin survey
69 | Los Angeles | Bellflower |  | Remove from POR | Remove from POR | Cancel pin survey
70 | Los Angeles | Burbank |  | Remove from POR | Remove from POR | Cancel pin survey
71 | Los Angeles | Corona |  | Remove from POR | Remove from POR | Cancel pin survey
72 | Los Angeles | Dana Point |  | Remove from POR | Remove from POR | Cancel pin survey
73 | Los Angeles | Downey |  | Remove from POR | Remove from POR | Cancel pin survey
74 | Los Angeles | Encino |  | Remove from POR | Remove from POR | Cancel pin survey
75 | Los Angeles | Fontana |  | Remove from POR | Remove from POR | Cancel pin survey
76 | Los Angeles | Hermosa Beach |  | Remove from POR | Remove from POR | Cancel pin survey
77 | Los Angeles | Highland Park |  | Remove from POR | Remove from POR | Cancel pin survey
78 | Los Angeles | Huntington Beach North |  | Remove from POR | Remove from POR | Cancel pin survey
79 | Los Angeles | Koreatown |  | Remove from POR | Remove from POR | Cancel pin survey
80 | Los Angeles | Newport Beach |  | Remove from POR | Remove from POR | Cancel pin survey
81 | Los Angeles | Playa Vista |  | Remove from POR | Remove from POR | Cancel pin survey
82 | Los Angeles | San Clemente |  | Remove from POR | Remove from POR | Cancel pin survey
83 | Los Angeles | Stonegate |  | Remove from POR | Remove from POR | Cancel pin survey
84 | Los Angeles | UCLA |  | Remove from POR | Remove from POR | Cancel pin survey
85 | Los Angeles | West Hollywood |  | Remove from POR | Remove from POR | Cancel pin survey
86 | Los Angeles | Yorba Linda |  | Remove from POR | Remove from POR | Cancel pin survey
87 | Louisville | Cherokee Triangle |  | Remove from POR | Remove from POR | Cancel pin survey
88 | Memphis | Midtown Memphis |  | Remove from POR | Remove from POR | Cancel pin survey
89 | Miami | Aventura |  | Remove from POR | Remove from POR | Cancel pin survey
90 | Miami | Brickell |  | Remove from POR | Remove from POR | Cancel pin survey
91 | Miami | Doral |  | Remove from POR | Remove from POR | Cancel pin survey
92 | Miami | Kendall |  | Remove from POR | Remove from POR | Cancel pin survey
93 | Miami | Pompano Beach |  | Remove from POR | Remove from POR | Cancel pin survey
94 | Miami | South Beach |  | Remove from POR | Remove from POR | Cancel pin survey
95 | Miami | Tamiami |  | Remove from POR | Remove from POR | Cancel pin survey
96 | Milwaukee | Wauwatosa |  | Remove from POR | Remove from POR | Cancel pin survey
97 | Minneapolis | DT Minneapolis |  | Remove from POR | Remove from POR | Cancel pin survey
98 | Minneapolis | Maple Grove |  | Remove from POR | Remove from POR | Cancel pin survey
99 | Nashville | Wedgewood Houston |  | Remove from POR | Remove from POR | Cancel pin survey
100 | New Orleans | Uptown New Orleans |  | Remove from POR | Remove from POR | Cancel pin survey
101 | Norfolk | Ghent |  | Remove from POR | Remove from POR | Cancel pin survey
102 | Norfolk | VB Town Center |  | Remove from POR | Remove from POR | Cancel pin survey
103 | NYC | Concourse | Bronx | Remove from POR | Remove from POR | Cancel Pin Survey
104 | NYC | Jamaica | Queens | Remove from POR | Remove from POR | Cancel Pin Survey
105 | NYC | Riverdale | Bronx | Remove from POR | Remove from POR | Cancel pin survey
106 | NYC | Flatbush | Brooklyn | Remove from POR | Remove from POR | Cancel pin survey
107 | NYC | West Hartford | CT | Remove from POR | Remove from POR | Cancel pin survey
108 | NYC | Plainview | Long Island | Remove from POR | Remove from POR | Cancel pin survey
109 | NYC | Glen Cove | Long Island | Remove from POR | Remove from POR | Cancel pin survey
110 | NYC | Great Neck | Long Island | Remove from POR | Remove from POR | Cancel pin survey
111 | NYC | Hackensack | NJ | Remove from POR | Remove from POR | Cancel pin survey
112 | NYC | East Rutherford | NJ | Remove from POR | Remove from POR | Cancel pin survey
113 | NYC | Woodland Park | NJ | Remove from POR | Remove from POR | Cancel pin survey
114 | NYC | Jackson Heights | Queens | Remove from POR | Remove from POR | Cancel pin survey
115 | NYC | Rochdale | Queens | Remove from POR | Remove from POR | Cancel pin survey
116 | NYC | Yonkers | Westchester County | Remove from POR | Remove from POR | Cancel pin survey
117 | NYC | Tarrytown | Westchester County | Remove from POR | Remove from POR | Cancel pin survey
118 | Oklahoma City | DT Oklahoma City |  | Remove from POR | Remove from POR | Cancel pin survey
119 | Orlando | DT Orlando |  | Remove from POR | Remove from POR | Cancel pin survey
120 | Orlando | Horizon West |  | Remove from POR | Remove from POR | Cancel pin survey
121 | Orlando | Lake Nona |  | Remove from POR | Remove from POR | Cancel pin survey
122 | Orlando | MetroWest |  | Remove from POR | Remove from POR | Cancel pin survey
123 | Philly | Trolley Square | DE | Remove from POR | Remove from POR | Cancel pin survey
124 | Philly | University City | PA | Remove from POR | Remove from POR | Cancel pin survey
125 | Philly | Pike Creek | DE | Remove from POR | Remove from POR | Cancel pin survey
126 | Philly | Haddonfield | NJ | Remove from POR | Remove from POR | Cancel pin survey
127 | Philly | Ardmore | PA | Remove from POR | Remove from POR | Cancel pin survey
128 | Philly | Mt Airy | PA | Remove from POR | Remove from POR | Cancel pin survey
129 | Philly | Rittenhouse Square | PA | Remove from POR | Remove from POR | Cancel pin survey
130 | Phoenix | Arrowhead |  | Remove from POR | Remove from POR | Cancel pin survey
131 | Phoenix | Santan Village |  | Remove from POR | Remove from POR | Cancel pin survey
132 | Pittsburgh | Dormont |  | Remove from POR | Remove from POR | Cancel pin survey
133 | Pittsburgh | DT Pittsburgh |  | Remove from POR | Remove from POR | Cancel pin survey
134 | DC - Baltimore | Alexandria West | VA | Remove from POR | Remove from POR | Cancel pin survey
135 | Portland | Boise |  | Remove from POR | Remove from POR | Cancel pin survey
136 | Raleigh | Brier Creek |  | Remove from POR | Remove from POR | Cancel pin survey
137 | Raleigh | Cary |  | Remove from POR | Remove from POR | Cancel pin survey
138 | Raleigh | North Hills |  | Remove from POR | Remove from POR | Cancel pin survey
139 | Richmond | Shockoe Bottom |  | Remove from POR | Remove from POR | Cancel pin survey
140 | Richmond | The Fan |  | Remove from POR | Remove from POR | Cancel pin survey
141 | Sacramento | Elk Grove |  | Remove from POR | Remove from POR | Cancel pin survey
142 | Salt Lake City | Cottonwood Heights |  | Remove from POR | Remove from POR | Cancel pin survey
143 | Salt Lake City | Daybreak |  | Remove from POR | Remove from POR | Cancel pin survey
144 | Salt Lake City | DT Salt Lake City |  | Remove from POR | Remove from POR | Cancel pin survey
145 | Salt Lake City | Lehi |  | Remove from POR | Remove from POR | Cancel pin survey
146 | Salt Lake City | Taylorsville |  | Remove from POR | Remove from POR | Cancel pin survey
147 | San Antonio | Alamo Heights |  | Remove from POR | Remove from POR | Cancel pin survey
148 | San Diego | North Park |  | Remove from POR | Remove from POR | Cancel pin survey
149 | San Diego | Del Mar |  | Remove from POR | Remove from POR | Cancel pin survey
150 | San Diego | Encinitas |  | Remove from POR | Remove from POR | Cancel pin survey
151 | San Diego | Hillcrest |  | Remove from POR | Remove from POR | Cancel pin survey
152 | San Diego | Pacific Beach |  | Remove from POR | Remove from POR | Cancel pin survey
153 | San Francisco | Berkeley | East Bay | Remove from POR | Remove from POR | Cancel pin survey
154 | San Francisco | Hayward | East Bay | Remove from POR | Remove from POR | Cancel pin survey
155 | San Francisco | Richmond | East Bay | Remove from POR | Remove from POR | Cancel pin survey
156 | San Francisco | Mill Valley | Marin County | Remove from POR | Remove from POR | Cancel pin survey
157 | San Francisco | Palo Alto | Peninsula | Remove from POR | Remove from POR | Cancel pin survey
158 | San Francisco | Central Richmond | SF | Remove from POR | Remove from POR | Cancel pin survey
159 | San Francisco | Hayes Valley | SF | Remove from POR | Remove from POR | Cancel pin survey
160 | San Francisco | Noe Valley | SF | Remove from POR | Remove from POR | Cancel pin survey
161 | San Francisco | Pacific Heights | SF | Remove from POR | Remove from POR | Cancel pin survey
162 | San Francisco | Rincon Hill | SF | Remove from POR | Remove from POR | Cancel pin survey
163 | San Francisco | Cupertino | South Bay | Remove from POR | Remove from POR | Cancel pin survey
164 | San Francisco | Santana Row | South Bay | Remove from POR | Remove from POR | Cancel pin survey
165 | San Francisco | San Ramon | Tri-Valley | Remove from POR | Remove from POR | Cancel pin survey
166 | San Francisco | Alameda | East Bay | Remove from POR | Remove from POR | Cancel pin survey
167 | Sarasota | DT Sarasota |  | Remove from POR | Remove from POR | Cancel pin survey
168 | Seattle | West Seattle | Seattle | Remove from POR | Remove from POR | Cancel pin survey
169 | Seattle | Bothell | Seattle | Remove from POR | Remove from POR | Cancel pin survey
170 | Seattle | Issaquah | Seattle | Remove from POR | Remove from POR | Cancel pin survey
171 | Seattle | Kirkland | Seattle | Remove from POR | Remove from POR | Cancel pin survey
172 | Seattle | New Castle | Seattle | Remove from POR | Remove from POR | Cancel pin survey
173 | Seattle | Redmond | Seattle | Remove from POR | Remove from POR | Cancel pin survey
174 | Seattle | University Place | Tacoma | Remove from POR | Remove from POR | Cancel pin survey
175 | St Louis | Central West End |  | Remove from POR | Remove from POR | Cancel pin survey
176 | Tucson | U of A |  | Remove from POR | Remove from POR | Cancel pin survey

## Sheet3 (hidden)
| Previous Plan |  |  | Proposed Plan |  |  |  |  | Pin Count Breakdown by Launch Risk
Metro | PDC | PDC/pin | Pin Count | PDC | PDC/pin | Pin Count | On POR | Active PDC | Launched | Low | Medium | High
NYC | 5.24% | 0.1% | 50 | 5.14% | 0.2% | 26 | 15 | 3.3% |  |  |  | 26
Los Angeles | 3.79% | 0.1% | 39 | 3.28% | 0.19% | 17 | 9 | 1.61% |  | 9 | 8
San Francisco | 2.13% | 0.09% | 25 | 1.93% | 0.24% | 8 | 3 | 0.7% |  | 1 | 2 | 5
DC - Baltimore | 1.88% | 0.1% | 19 | 1.62% | 0.16% | 10 | 3 | 0.54% |  | 3 |  | 7
Miami | 1.93% | 0.12% | 16 | 1.49% | 0.21% | 7 | 5 | 0.98% |  | 6 | 1
Dallas | 1.47% | 0.13% | 11 | 1.42% | 0.2% | 7 | 6 | 1.05% | 4 | 3
Chicago | 1.59% | 0.08% | 19 | 1.12% | 0.19% | 6 | 6 | 1.12% |  | 6
Houston | 1.63% | 0.1% | 17 | 1.08% | 0.19% | 6 | 6 | 1.08% |  | 6
San Diego | 1.08% | 0.1% | 11 | 1.04% | 0.21% | 5 | 2 | 0.39% |  |  |  | 5
Seattle | 1.12% | 0.07% | 15 | 0.93% | 0.16% | 6 | 4 | 0.76% | 4 | 2
Phoenix | 1.34% | 0.12% | 11 | 0.91% | 0.15% | 6 | 5 | 0.83% | 1 | 5
Boston | 0.78% | 0.08% | 10 | 0.75% | 0.12% | 6 | 2 | 0.22% |  | 2 | 4
Minneapolis | 0.73% | 0.15% | 5 | 0.68% | 0.23% | 3 | 1 |  | 1 | 2
Las Vegas | 0.73% | 0.18% | 4 | 0.68% | 0.23% | 3 | 2 |  |  | 3
Denver | 0.9% | 0.1% | 9 | 0.63% | 0.21% | 3 | 3 |  |  | 3
Salt Lake City | 0.65% | 0.08% | 8 | 0.6% | 0.2% | 3 | 1 |  |  | 3
Atlanta | 0.65% | 0.09% | 7 | 0.58% | 0.12% | 5 | 3 |  | 2 | 3
Sacramento | 0.66% | 0.09% | 7 | 0.56% | 0.28% | 2 | 1 |  |  |  | 2
Philly | 1.34% | 0.09% | 15 | 0.55% | 0.14% | 4 | 3 |  | 3 | 1
Portland | 0.63% | 0.1% | 6 | 0.55% | 0.18% | 3 | 3 |  |  | 3
Austin | 0.58% | 0.12% | 5 | 0.55% | 0.18% | 3 | 3 |  | 1 | 2
Detroit | 0.63% | 0.13% | 5 | 0.44% | 0.22% | 2 | 1 |  |  | 2
Tampa | 0.44% | 0.15% | 3 | 0.41% | 0.21% | 2 | 2 |  |  | 2
San Antonio | 0.39% | 0.13% | 3 | 0.38% | 0.19% | 2 | 1 |  |  | 2
Orlando | 0.62% | 0.09% | 7 | 0.37% | 0.18% | 2 | 1 |  | 1 |  | 1
St Louis | 0.37% | 0.12% | 3 | 0.32% | 0.16% | 2 | 2 |  |  | 2
Kansas City | 0.36% | 0.09% | 4 | 0.31% | 0.15% | 2 | 1 |  |  | 2
Indianapolis | 0.41% | 0.1% | 4 | 0.29% | 0.15% | 2 | 2 |  |  | 2
Milwaukee | 0.28% | 0.09% | 3 | 0.26% | 0.26% | 1 | 1 |  |  | 1
Providence | 0.21% | 0.21% | 1 | 0.21% | 0.21% | 1 | 1 |  |  | 1
Oklahoma City | 0.32% | 0.08% | 4 | 0.2% | 0.2% | 1 | 1 |  | 1
Raleigh | 0.5% | 0.1% | 5
Norfolk | 0.42% | 0.11% | 4
Columbus | 0.4% | 0.13% | 3
Charlotte | 0.36% | 0.12% | 3
Cleveland | 0.32% | 0.11% | 3
Cincinnati | 0.29% | 0.15% | 2
Pittsburgh | 0.28% | 0.09% | 3
Nashville | 0.27% | 0.07% | 4
Jacksonville | 0.25% | 0.12% | 2
Boise | 0.25% | 0.08% | 3
Richmond | 0.22% | 0.11% | 2
Louisville | 0.21% | 0.11% | 2
Des Moines | 0.19% | 0.09% | 2
New Orleans | 0.18% | 0.09% | 2
Buffalo | 0.18% | 0.09% | 2
Tucson | 0.18% | 0.18% | 1
Charleston | 0.14% | 0.07% | 2
Birmingham | 0.13% | 0.07% | 2
Sarasota | 0.13% | 0.13% | 1
Memphis | 0.1% | 0.1% | 1
Total | 39.88% | 0.1% | 395 | 29.41% | 0.19% | 156 | 99 |  | 18 | 77 | 18 | 43